## Read Me
SFH DEVELOPMENT - QUANTITY TAKEOFF & PRELIMINARY ESTIMATE
Project | SFH Development - single-family spec home (Sidney Aulds Building Studio)
Owner | Chris Hill
Location | Ouachita Parish, Louisiana (address TBD - drawings 'Enter address here')
Building | 1-story, slab-on-grade, 2 bed / 2 bath. 1,352 gsf conditioned + 117 gsf porch + 504 gsf covered parking = 1,973 gsf (design notes)
Estimate purpose / class | Preliminary budget estimate (AACE Class 4-ish, schematic/progress drawings). NOT a bid. Expected accuracy roughly -15% / +25%.
Drawings used | 2305031 Progress Drawings dated 5/31/2023 - G000 (cover), A100, A101, A401, A701 - stamped 'NOT FOR CONSTRUCTION'; Spec Home Schematic Design Notes (3 pp).
Estimate date / price date | 2026-10-15
Units / currency | US customary units (ft, SF, LF, CY, SQ = 100 SF, EA, LS); USD
Pricing basis | Estimator budget unit costs for the Monroe/Ouachita Parish market, Q4-2026. Material costs are pre-tax. These are NOT supplier or subcontractor quotes - replace with local quotes before contracting.
Markups | Sales tax, contingency, overhead and profit are INPUT cells on the Summary sheet (markup on cost). Defaults are placeholders - confirm.
Status | PRELIMINARY - quantities and costs require estimator review. Open RFIs listed on 'Assumptions & RFIs'.
Workflow | Drawing Register -> Takeoff Detail (dims & formulas) -> Cost Database (unit costs w/ source/date) -> Estimate Detail (qty pulled by INDEX/MATCH from takeoff, unit costs from DB) -> Summary (SUMIFS by division + markups) -> Reconciliation (takeoff vs 3D model vs design notes).
3D model | output/model/SFH_3D_Model.html - every model element carries the takeoff ID used in this workbook.
Regenerate | python3 scripts/build_estimate.py then scripts/build_all.sh (recalculates with LibreOffice and rebuilds the model).
COLOR KEY
Blue text / blue fill | Hard-coded input (dimension, count, unit price, markup %) - edit these
Black text | Formula / calculation - do not overwrite
Green text | Link pulled from another sheet
Yellow row fill | Basis = Assumed or Allowance (not measured from drawings)
Orange row fill | Confidence = Low - review before use

## Summary
SFH DEVELOPMENT - PRELIMINARY CONSTRUCTION ESTIMATE
Ouachita Parish, LA ¦ Progress drawings 5/31/2023 (Not for construction) ¦ Price date 2026-10-15 ¦ Budget estimate - not a bid
| Conditioned area (gsf, design notes) | 1352 |  | Sales tax on materials |  | 10% | ASSUMED - verify Ouachita rate for address
| Front porch (gsf) | 117 |  | Contingency (on cost) |  | 5% | placeholder
| Covered parking (gsf) | 504 |  | Overhead (on cost) |  | 8% | placeholder
| Total under roof (gsf) | 1973 |  | Profit (on cost) |  | 10% | placeholder
Div | Division | Material $ | Labor $ | Sub/Equip $ | Total $ | $ / Cond. SF | % of Direct
01 | General Requirements | 1413.255 | 14018.58 | 15516.5125 | 30948.3475 | 22.8908 | 12.1%
31 | Earthwork | 2907 | 368 | 6305.785 | 9580.785 | 7.0864 | 3.747%
03 | Concrete | 12009.263 | 7346.4397 | 5074 | 24429.7027 | 18.0693 | 9.555%
06 | Wood & Rough Carpentry | 25289.7437 | 12125.3125 | 1150 | 38565.0562 | 28.5244 | 15.08%
07 | Thermal & Moisture Protection | 12969.6679 | 12228.795 | 5876.7605 | 31075.2234 | 22.9846 | 12.15%
08 | Openings | 10415 | 2752 | 0 | 13167 | 9.7389 | 5.15%
09 | Finishes | 7388.183 | 18569.4685 | 0 | 25957.6515 | 19.1994 | 10.15%
10 | Specialties | 993 | 599 | 0 | 1592 | 1.1775 | 0.6226%
11 | Equipment (Appliances) | 85 | 350 | 0 | 435 | 0.32175 | 0.1701%
12 | Casework & Countertops | 8669.14 | 1776.5 | 0 | 10445.64 | 7.7261 | 4.085%
22 | Plumbing | 7150 | 8355 | 275 | 15780 | 11.6716 | 6.172%
23 | HVAC | 7429.125 | 4567.25 | 175 | 12171.375 | 9.0025 | 4.76%
26 | Electrical | 7673.3375 | 8910.1125 | 225 | 16808.45 | 12.4323 | 6.574%
32 | Exterior Improvements | 8077.6428 | 8258.8196 | 1200 | 17536.4624 | 12.9708 | 6.859%
33 | Utilities | 0 | 0 | 7190 | 7190 | 5.318 | 2.812%
| TOTAL DIRECT COST | 112469.3579 | 100225.2778 | 42988.058 | 255682.6937 | 189.1144 | 100%
| Sales tax on materials |  |  |  | 11246.9358 | 8.3187
| Subtotal with tax |  |  |  | 266929.6295 | 197.4332
| Contingency |  |  |  | 13346.4815 | 9.8717
| Overhead |  |  |  | 22422.0889 | 16.5844
| Profit |  |  |  | 30269.82 | 22.3889
| GRAND TOTAL (budget) |  |  |  | 332968.0199 | 246.2781
| Grand total per SF under roof (1,973 gsf) |  |  |  | 168.7623
Excluded: land, financing & closing, sales commissions, appliances & W/D (owner), window coverings, fencing, irrigation, septic, gas service, security/AV, solar, architect fees, builder's warranty reserve, escalation beyond price date, rock/unsuitable soil removal, flood elevation above 12" pad.

## Drawing Register
Sheet | Title | Discipline | Scale | Revision / Date | Status | File / Page | Used for | Notes / Issues
G000 | Cover sheet (rendering, project team) | General | NTS | Progress 5/31/2023 | Not for construction | 2305031_Progress_Drawings.pdf p1 | Massing check (rendering) | No sheet number printed on page; design notes call it G000. Project team blank (no structural/MEP engineers).
A100 | Site plan | Architectural | 1/16" = 1'-0" | Progress 5/31/2023 | Not for construction | p2 | Lot 50' x 180', setbacks, driveway | Design notes list 'A100 - Plans'; set has A100 = Site Plan, A101 = Plans (numbering conflict, RFI-16). Address 'Enter address here'.
A101 | Plans: finish floor, finish floor RCP, T.O. plate (roof) | Architectural | 1/8" = 1'-0" | Progress 5/31/2023 | Not for construction | p3 | Primary takeoff: overall dims 21'-0" x 70'-0" + 24'-0" carport, room chain, partitions, RCP ceiling heights & fixtures | Calibrated: 21'-0" = 395 px @150 dpi (18.81 px/ft); vertical chain 70'-0" = 1,312 px (18.74 px/ft) - 0.4% check. Interior partitions not dimensioned (SCALED).
A401 | Building elevations A-D | Architectural | 1/4" = 1'-0" | Progress 5/31/2023 | Not for construction | p4 | T.O. plate 9'-0", 6/12 pitch, cladding types, window/door tags, gutters | Overhangs not dimensioned (ASSUMED 12").
A701 | Schedules & details (door/window schedules, types) | Architectural | NTS | Progress 5/31/2023 | Not for construction | p5 | Door & window counts/sizes | Door 01 R1 4'-0" x 8'-0" leaf/sidelite split not dimensioned.
Notes | Spec Home Schematic Design Notes | Narrative spec | — | Undated | Schematic | Spec_Home_Schematic_Design_Notes.pdf (3 pp) | Finishes, framing, sheathing, HVAC, areas | Areas: porch 117, conditioned 1,352, covered parking 504, total 1,973 gsf.
— | Structural drawings | Structural | — | MISSING | Not issued | — | — | Foundation, beams, trusses: ASSUMED. RFI-05.
— | MEP drawings | MEP | — | MISSING | Not issued | — | — | HVAC, electrical, plumbing priced as design-build allowances.

## Assumptions & RFIs
ID | Category | Question / Issue | Assumption used in this estimate | Qty / cost impact | Responsible | Status | Resolution
RFI-01 | Site | Property address, survey, topography, flood zone, utility locations and street type (curb vs. open ditch) are not provided ('Enter address here'). | Typical in-town Ouachita Parish lot 50' x 180' per A100, lightly treed, public water & sewer at the street, open-ditch possible. | 31-100 clearing, 32-130 culvert, 33-1xx utilities are allowances (~$13k combined). | Owner | Open
RFI-02 | Permits | Permitting jurisdiction (City of Monroe, City of West Monroe, or unincorporated Ouachita Parish) and fee schedule. | Permit & plan review allowance $2,600 plus trade permits. | 01-100, 22-195, 23-160, 26-350 | Owner/GC | Open
RFI-03 | Energy code | Insulation R-values, fenestration U-factor/SHGC and testing requirements are not specified. | R-21 walls, R-38 ceiling, standard Low-E vinyl windows, blower-door/duct test allowance. | 07-100/110, 01-210 | Architect | Assumed
RFI-04 | Geotechnical | No soils report. NE Louisiana clays are often expansive; slab design and pad height depend on PI and flood elevation. | 12" average select-fill pad, 5' beyond slab, conventional reinforced monolithic slab. Geotech allowance carried. | 31-120 (149 CY loose), 03-1xx, 01-106. A post-tensioned or stiffened slab could change foundation cost +/- $4-8k. | Owner/Engineer | Open
RFI-05 | Structural | No structural drawings (project team lists none). Foundation, beam, header and connector design are by others. | 4" slab, 12"x24" perimeter beam (4 #5), 12"x20" interior beams on ~20' grid, #3 @ 18" EW, (2) 2x10 headers. | 03-100..150, 06-130 | Engineer | Open
RFI-06 | Roof framing | Design notes call for 'cambered roof truss 4' O.C.' with ZIP roof sheathing. ZIP roof panels are typically span-rated for 24" supports, and 5/8" gypsum ceilings need supports at 24" max. | Trusses at 48" O.C. as noted PLUS 2x4 roof purlins @ 24" and 2x4 ceiling furring @ 24". Alternative: trusses @ 24" O.C. (~+21 trusses, -purlins/furring). | 06-190..220. Purlins + furring ~ $2.0k material + labor in framing rate. | Architect/Truss mfr. | Open
RFI-07 | Structural | Covered parking has posts only at the two rear corners (A101/A401): 24' clear-span eave beams required. Open porch front also needs a ~21' beam. | 3-1/2" x 14" LVL (2-ply) both carport eaves and porch front; 6x6 PT posts on 24" footings. | 06-250 (72 LF), 06-260, 03-220 | Engineer | Open
RFI-08 | Roof geometry | Eave and rake overhangs are not dimensioned. A401 scales to roughly 8-12". | 12" eave and 12" rake overhang on all sides; boxed, vented FC soffit. | Roof area, fascia, soffit, gutters (each +/-3%). | Architect | Assumed
RFI-09 | Cladding | Design notes conflict: 'lap siding front porch' vs 'Fiber Cement Tongue & Groove Siding (continued to ceiling)'. A401 Elev B says 'Fiber cement T&G siding'. | Fiber cement T&G (per A401) at porch walls, front gable and porch ceiling. | 07-160/170 (~$3.0k). | Architect | Open
RFI-10 | Code/egress | Bedroom egress: Type B 6'-0" x 4'-0" casement at 3'-0" sill. Confirm clear opening/sill height meet egress. | Type B casement as scheduled (twin casement). | None if compliant. | Architect | Open
RFI-11 | Code/glazing | Type D windows adjacent to door 01 and the door 01 sidelite may require safety glazing. | Door 01 sidelite tempered (in door price); D windows standard glass. | Tempered D windows ~+$150 ea. | Architect | Open
RFI-12 | Doors | Door 01 (R1) is scheduled 4'-0" x 8'-0" but leaf vs. sidelite split is not dimensioned (A701 shows 4'-0" and 2'-0" marks). Door material not specified (frame wood). | 3'-0" x 8'-0" leaf + 1'-0" sidelite, prehung, fiberglass or wood. | 08-200 | Architect | Open
RFI-13 | Casework | Kitchen layout scaled from plan: tall element at west end of back run (pantry vs. refrigerator) and dishwasher location are not labeled. No laundry cabinets shown. | Tall pantry west end, refrigerator east end, DW in island next to sink, no laundry cabinets. | 12-100..130 | Architect/Owner | Open
RFI-14 | HVAC | Air handler location, heat source (heat pump vs. gas) and duct route not shown. No gas service indicated. | All-electric: 2-ton heat pump, horizontal air handler in attic over hall, duct trunk in attic. | 23-1xx | Owner/HVAC | Open
RFI-15 | Electrical | No electrical plan: device counts, service size, panel location. | 200A service, panel in storage, code-minimum device layout (~64 devices); lights per RCP; 6 soffit downlights. | 26-1xx | Owner/Electrician | Open
RFI-16 | Documents | Design notes list sheets G000, A100 'Plans', A401, A701; the drawing set contains A100 'Site Plan' and A101 'Plans'. Drawings are a progress set marked NOT FOR CONSTRUCTION (5/31/2023). | Used the 5/31/2023 set as latest; A101 governs plan dimensions. | Re-check quantities when CDs are issued. | Architect | Open
RFI-17 | Finishes | Interior base, casing and window trim are not specified. | 3-1/4" MDF base, 2-1/4" MDF casing, drywall-return windows with MDF stool & apron, all painted. | 09-200..220 | Architect/Owner | Assumed
RFI-18 | Finishes | Finished concrete floors: smooth trowel finish - confirm level (polish grit / sealer / stain) and slab protection responsibility. Interior control joints will be visible. | Hard-trowel + light grind, densifier, penetrating sealer; Ram Board protection through construction. | 03-180, 01-180 | Owner | Open
RFI-19 | Areas | Design-notes conditioned area 1,352 gsf vs. dimensioned 21'-0" x 64'-2" = 1,347.5 SF; porch 117 gsf (inside walls) vs. 124.3 SF slab. | Quantities use dimensioned values; $/SF metrics use design-notes gsf. | <0.5% / 6% - see Reconciliation. | Estimator | Assumed
RFI-20 | Plumbing | Water heater size/fuel not specified; WH symbol in storage. Kitchen sink is in the island (venting method, e.g. AAV/loop vent, to be confirmed). | 50 gal electric tank WH; island sink vented per plumber (included in rough). | 22-100, 22-150 | Plumber | Assumed
RFI-21 | Exterior | Porch hatched element at east end of porch (A101) is not labeled. | Not priced (assumed furniture/bench by owner). | Possible built-in storage closet ~$1.5k if required. | Architect | Open
RFI-22 | Exterior paint | Fiber cement finish: factory-primed vs. pre-finished (e.g., ColorPlus) not specified. | Primed product, field painted (09-260/265). | Pre-finished could save ~$3-4k paint, add ~$1.5k material. | Owner | Assumed
A-01 | Wall heights | All walls framed to 9'-0" T.O. plate (A401). Rooms with 8'-0" ceilings get dropped ceiling joists. | 104-5/8" precut studs, 9' drywall walls everywhere (slight over-measure in 8' rooms). |  | Estimator | Assumed
A-02 | Openings | Opening deductions: siding and drywall deduct actual window/door areas; sheathing does not (cut waste). Waste factors applied separately per line. |  |  | Estimator | Assumed
A-03 | Pricing | Unit costs are estimator budget values for the Monroe/Ouachita market at 2026-10-15, pre-tax materials, open-shop labor. Not quotes. | Sales tax 10% on materials placeholder; contingency 5%, overhead 8%, profit 10% (on cost) placeholders. | Summary inputs. | Owner/GC | Assumed
A-04 | Schedule | Construction duration ~5 months (20 weeks) for general conditions. |  | 01-130/140/160 | GC | Assumed
A-05 | Owner items | Appliances (range, refrigerator, OTR microwave, dishwasher) and washer/dryer supplied by owner per design notes; contractor installs/hooks up. |  | 11-100 = $0; 11-110 hookup allowance. | Owner | Assumed

## Takeoff Detail
ID | Cost Code | Division | Description | Spec / Reference | Sheet | Location | Takeoff Type | Count | Length (ft) | Width / Ht (ft) | Depth (ft) | Factor | Deduct | Net Qty | Unit | Waste % | Gross Qty | Round Up? | Calculation / Method | Basis | Confidence | Notes / Assumptions
01-100 | 01 | General Requirements | Building permit & plan review | Ouachita Parish / municipal residential permit | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium | Jurisdiction depends on final address (City of Monroe, West Monroe or unincorporated Ouachita). RFI-02.
01-105 | 01 | General Requirements | Engineering: foundation design, carport/porch beams, truss review | Licensed LA engineer letter/stamp | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium | No structural drawings in set. RFI-05/06/07.
01-106 | 01 | General Requirements | Geotechnical investigation (borings, PI, slab recommendations) | Recommended for NE LA expansive clays | — | Site | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium | RFI-04
01-110 | 01 | General Requirements | Survey: boundary, staking, form-board, final as-built |  | A100 | Site | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-120 | 01 | General Requirements | Temporary power pole, connection & usage |  | — | Site | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-125 | 01 | General Requirements | Temporary water & usage |  | — | Site | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-130 | 01 | General Requirements | Portable toilet |  | — | Site | Count | 5 | [5 empty] | 5 | MO | 0% | 5 | N | 5 month schedule | Assumed | Medium | Schedule ASSUMED 5 months.
01-140 | 01 | General Requirements | Dumpster, 20 CY, haul & dump |  | — | Site | Count | 5 | [5 empty] | 5 | EA | 0% | 5 | N | ~1 pull per month | Assumed | Medium
01-150 | 01 | General Requirements | Builder's risk insurance |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-160 | 01 | General Requirements | Site supervision (part-time superintendent) |  | — | Project | Count | 20 | [5 empty] | 20 | WK | 0% | 20 | N | 20 weeks x part-time super | Assumed | Medium
01-170 | 01 | General Requirements | Final construction clean incl. windows |  | A101 | All areas | Area | 1 | 21 | 94.0833 |  |  |  | 1975.75 | SF | 0% | 1975.75 | N | 21' x 94.08' under roof | Calculated | High
01-175 | 01 | General Requirements | Periodic jobsite cleanup |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-180 | 01 | General Requirements | Finished-slab protection (Ram Board/taped) - smooth trowel floors | Design notes: concrete floors are the finish | Notes | Conditioned | Area |  | 21 | 64.1667 |  |  |  | 1347.5 | SF | 10% | 1482.25 | N | 21' x 64.17' | Calculated | High | Required because finished floor is exposed concrete.
01-190 | 01 | General Requirements | Termite pre-treatment & LDAF certificate | Louisiana pre-construction termite treatment | — | Slab | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-200 | 01 | General Requirements | Small tools & consumables |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
01-210 | 01 | General Requirements | Energy code testing (blower door / duct leakage) |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium | Verify requirement with AHJ (RFI-03).
31-100 | 31 | Earthwork | Clear & grub, strip topsoil (building & drive area) |  | A100 | Site | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Low | Lot condition unknown (address TBD). RFI-01.
31-120 | 31 | Earthwork | Select fill building pad, 12" avg, compacted (loose CY incl. 25% shrink) | Slab footprint + 5' each side | A101 | Building pad | Volume |  | 31 | 104.0833 | 1 | 0.037037 |  | 119.5031 | CY | 25% | 150 | Y | (21+10) x (94.08+10) x 1.0' / 27 | Assumed | Low | Pad height ASSUMED 12" avg; set by survey/geotech & flood zone. RFI-04.
31-130 | 31 | Earthwork | Fine grade building pad |  | A101 | Building pad | Area |  | 31 | 104.0833 |  |  |  | 3226.5833 | SF | 0% | 3226.5833 | N | 31' x 104.08' | Calculated | High
31-140 | 31 | Earthwork | Final grading & topsoil spread |  | A100 | Lot | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
31-150 | 31 | Earthwork | Silt fence / erosion control |  | A100 | Lot perimeter (front & sides) | Length |  | 230 |  |  |  |  | 230 | LF | 0% | 230 | N | front 50' + 2 sides x 90' | Assumed | Medium
03-100 | 03 | Concrete | Slab-on-grade 4" (house, porch, carport) - concrete | 3000 psi ready-mix | A101 | Footprint 21' x 94.08' | Volume |  | 21 | 94.0833 | 0.33333 | 0.037037 |  | 24.392 | CY | 5% | 25.6116 | N | 21' x (70.08'+24') x 0.333' / 27 | Calculated | High | Slab thickness ASSUMED 4" (no structural). Footprint DIM.
03-110 | 03 | Concrete | Perimeter grade beam 12" w x 20" below slab - concrete | Monolithic | A101 | Perimeter | Volume |  | 230.1667 | 1 | 1.6667 | 0.037037 |  | 14.2078 | CY | 8% | 15.3444 | N | 2 x (21 + 94.08) LF x 1.0' x 1.667' / 27 | Assumed | Medium | Beam size ASSUMED typical NE LA; engineer to confirm.
03-120 | 03 | Concrete | Interior grade beams 12" w x 16" below slab - concrete |  | A101 | 5 transverse + 1 longitudinal | Volume |  | 187.0833 | 1 | 1.3333 | 0.037037 |  | 9.2387 | CY | 8% | 9.9778 | N | (5 x 19' + 92.08') x 1.0' x 1.333' / 27 | Assumed | Low | Layout ASSUMED ~20' grid.
03-130 | 03 | Concrete | Vapor retarder 10 mil poly, lapped & taped |  | A101 | Under slab | Area |  | 21 | 94.0833 |  |  |  | 1975.75 | SF | 15% | 2272.1125 | N | 21' x 94.08' (+15% laps/beam sides) | Calculated | High
03-140 | 03 | Concrete | Rebar #5 continuous in grade beams (4 bars) | Grade 60 | A101 | All beams | Length | 4 | 417.25 |  |  |  |  | 1669 | LF | 10% | 1835.9 | N | 4 bars x (230.17 + 187.08) LF | Assumed | Medium
03-150 | 03 | Concrete | Rebar #3 @ 18" O.C. each way in slab | Grade 60 | A101 | Slab | Length |  | 21 | 94.0833 |  | 1.3333 |  | 2634.3333 | LF | 10% | 2897.7667 | N | 1975.7 SF x (2 / 1.5 ft) LF/SF | Assumed | Medium
03-160 | 03 | Concrete | Forms, chairs, stakes, ties, edge/expansion material |  | A101 | Slab | Area |  | 21 | 94.0833 |  |  |  | 1975.75 | SF | 0% | 1975.75 | N | slab area | Calculated | High
03-170 | 03 | Concrete | Foundation labor: form, set steel, place & finish (sub) |  | A101 | Slab | Area |  | 21 | 94.0833 |  |  |  | 1975.75 | SF | 0% | 1975.75 | N | slab area | Calculated | High
03-175 | 03 | Concrete | Concrete pump truck |  | — | Slab pour | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
03-180 | 03 | Concrete | Finished concrete floors: smooth trowel premium, grind, densifier & sealer | Design notes: Concrete, smooth trowel (all rooms) | Notes / A101 | Conditioned | Area |  | 21 | 64.1667 |  |  |  | 1347.5 | SF | 0% | 1347.5 | N | 21' x 64.17' | Calculated | High
03-185 | 03 | Concrete | Porch slab: smooth trowel, slope away, sealer | Design notes | Notes / A101 | Front porch | Area |  | 21 | 5.9167 |  |  |  | 124.25 | SF | 0% | 124.25 | N | 21' x 5.92' | Calculated | High
03-190 | 03 | Concrete | Anchor bolts / sill anchors at exterior walls |  | A101 | Exterior walls | Count | 46 | [5 empty] | 46 | EA | 0% | 46 | N | 182.2 LF / 6' O.C. + 2 per plate piece (~8 pcs) | Calculated | Medium
03-200 | 03 | Concrete | Saw-cut control joints |  | A101 | Slab | Length |  | 120 |  |  |  |  | 120 | LF | 0% | 120 | N | ~5 joints x 21' + porch | Assumed | Medium
03-220 | 03 | Concrete | Carport post footings 24"x24"x24" w/ post base |  | A101 | Carport corners | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N | 2 posts shown | Measured | Medium | Footing size ASSUMED.
06-100 | 06 | Wood & Rough Carpentry | PT 2x6 bottom/sill plate - exterior walls |  | A101 | Exterior walls | Length |  | 182.17 |  |  |  |  | 182.17 | LF | 10% | 200.387 | N | 2 x 70.08 + 2 x 21 | Calculated | High
06-110 | 06 | Wood & Rough Carpentry | 2x6 double top plate - exterior walls |  | A101 | Exterior walls | Length | 2 | 182.17 |  |  |  |  | 364.34 | LF | 10% | 400.774 | N | 2 plates x 182.17 LF | Calculated | High
06-120 | 06 | Wood & Rough Carpentry | 2x6 x 104-5/8" studs @ 24" O.C. - exterior walls | Design notes: 2x6 ext walls @ 24" O.C. | Notes / A101 | Exterior walls | Count | 208 | [5 empty] | 208 | EA | 10% | 229 | Y | LF/2 + corners 4x3 + partition T's 10x2 + 14 openings x4 (king+jack) + ~28 cripples | Calculated | Medium
06-130 | 06 | Wood & Rough Carpentry | 2x10 header stock, 2-ply - exterior openings |  | A701 | Exterior openings | Length | 2 | 69 |  |  |  |  | 138 | LF | 10% | 151.8 | N | 2 ply x Σ(opening width + 6"); D windows ganged on one 9.5' header | Calculated | Medium | Header sizes ASSUMED (no structural).
06-140 | 06 | Wood & Rough Carpentry | PT 2x4 bottom plate - interior partitions |  | A101 | Partitions | Length |  | 138.56 |  |  |  |  | 138.56 | LF | 10% | 152.416 | N | Σ partitions P1-P10 (SCALED/DIM) | Measured | Medium
06-150 | 06 | Wood & Rough Carpentry | 2x4 double top plate - interior partitions |  | A101 | Partitions | Length | 2 | 138.56 |  |  |  |  | 277.12 | LF | 10% | 304.832 | N | 2 x partition LF | Calculated | High
06-160 | 06 | Wood & Rough Carpentry | 2x4 x 104-5/8" studs @ 24" O.C. - partitions | Design notes: 2x4 int walls @ 24" O.C. | Notes / A101 | Partitions | Count | 142 | [5 empty] | 142 | EA | 10% | 157 | Y | LF/2 + wall ends 10x2 + intersections 12x2 + 7 doors x4 | Calculated | Medium
06-170 | 06 | Wood & Rough Carpentry | Interior door headers / misc 2x6 |  | A701 | Interior doors | Length |  | 60 |  |  |  |  | 60 | LF | 0% | 60 | N | 7 doors + misc | Assumed | Medium
06-180 | 06 | Wood & Rough Carpentry | Blocking & backing (cabinets, tubs, accessories, TV, grab-bar ready) |  | A101 | Interior | Length |  | 250 |  |  |  |  | 250 | LF | 0% | 250 | N |  | Allowance | Medium
06-190 | 06 | Wood & Rough Carpentry | Roof trusses - common 6/12, 21' span, flat bottom chord @ 4' O.C. | Design notes: cambered roof truss 4' O.C. | Notes / A401 | Over conditioned area | Count | 17 | [5 empty] | 17 | EA | 0% | 17 | N | 64.17'/4 + 1 = 17 | Calculated | Medium | Truss profile/camber by manufacturer. RFI-06.
06-191 | 06 | Wood & Rough Carpentry | Roof trusses - vaulted (parallel-chord) 6/12 for sloped carport/porch ceilings | A101 RCP: sloped ceilings 6"/1'-0" | A101 RCP | Carport & porch | Count | 6 | [5 empty] | 6 | EA | 0% | 6 | N | carport 5 + porch 1 | Calculated | Medium
06-192 | 06 | Wood & Rough Carpentry | End trusses at open gables (vaulted, w/ rake outlookers) |  | A401 | Carport & porch ends | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N | 2 ends | Calculated | Medium
06-200 | 06 | Wood & Rough Carpentry | 2x4 roof purlins @ 24" O.C. (flat) over 48" trusses | Needed to span 5/8" ZIP roof at 48" O.C. | Notes | Roof | Length | 14 | 96.08 |  |  |  |  | 1345.12 | LF | 10% | 1479.632 | N | 2 slopes x 7 lines (12.86' slope / 2') x 96.08' | Assumed | Low | RFI-06: confirm 48" truss spacing vs sheathing span rating.
06-210 | 06 | Wood & Rough Carpentry | 2x4 ceiling furring @ 24" O.C. under trusses (conditioned) | 5/8" GWB cannot span 48" | Notes | Conditioned ceiling | Length | 10 | 63.08 |  |  |  |  | 630.8 | LF | 10% | 693.88 | N | 10 lines x 63.08' | Assumed | Medium
06-215 | 06 | Wood & Rough Carpentry | 2x4 ceiling joists & ledgers for 8' ceilings | A101 RCP: 8'-0" ceilings | A101 RCP | Storage, closets, baths | Length |  | 153.94 |  |  |  |  | 153.94 | LF | 10% | 169.334 | N | 220 SF of 8' ceilings / 2' O.C. x 1.4 (ledgers) | Calculated | Medium
06-220 | 06 | Wood & Rough Carpentry | 2x4 nailers for sloped carport & porch ceilings |  | A101 RCP | Carport & porch | Length | 13 | 29.92 |  |  |  |  | 388.96 | LF | 10% | 427.856 | N | 13 lines x 29.92' | Assumed | Medium
06-230 | 06 | Wood & Rough Carpentry | Truss permanent lateral & diagonal bracing |  | — | Roof | Length |  | 400 |  |  |  |  | 400 | LF | 0% | 400 | N |  | Allowance | Medium
06-240 | 06 | Wood & Rough Carpentry | 2x6 sub-fascia |  | A401 | Eaves & rakes | Length |  | 243.6 |  |  |  |  | 243.6 | LF | 10% | 267.96 | N | 2 x 96.08 + 4 x 12.86 | Calculated | High
06-245 | 06 | Wood & Rough Carpentry | 2x4 soffit framing / lookouts |  | A401 | Eaves & rakes | Length |  | 200 |  |  |  |  | 200 | LF | 0% | 200 | N |  | Allowance | Medium
06-250 | 06 | Wood & Rough Carpentry | LVL beams 3-1/2" x 14" (carport eaves 2 x 25', porch front 22') | No structural; 24' clear span | A101 / A401 | Carport & porch | Length |  | 72 |  |  |  |  | 72 | LF | 0% | 72 | N | 2 x 25' + 22' | Assumed | Low | Size ASSUMED - engineer to design (RFI-07).
06-260 | 06 | Wood & Rough Carpentry | 6x6 PT posts w/ base & cap, wrapped |  | A101 | Carport corners | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N | 2 posts shown on A101 | Measured | Medium
06-270 | 06 | Wood & Rough Carpentry | ZIP System 7/16" wall sheathing, 4x9 panels | Design notes: Huberwood ZIP wall sheathing | Notes / A401 | Exterior walls + gables | Area | [6 empty] | 48.604 | SHT | 10% | 54 | Y | (2x70.08x9 + 2x21x9 + 2 gables 55.13) / 36 SF per sheet (openings not deducted - cut waste) | Calculated | High
06-280 | 06 | Wood & Rough Carpentry | ZIP System 5/8" roof sheathing, 4x8 panels | Design notes: ZIP roof sheathing | Notes / A401 | Roof | Area | [6 empty] | 77.2087 | SHT | 10% | 85 | Y | 96.08' x 11.5' x 1.118 x 2 / 32 | Calculated | High
06-290 | 06 | Wood & Rough Carpentry | ZIP System tape 3.75" x 90' rolls | ~7 panels per roll (Huber) | Notes | Wall & roof seams | Count | [6 empty] | 19.8571 | RL | 0% | 20 | Y | (wall + roof sheets) / 7 | Calculated | High
06-295 | 06 | Wood & Rough Carpentry | ZIP liquid flash / stretch tape at openings & penetrations |  | A701 | Openings | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
06-300 | 06 | Wood & Rough Carpentry | Structural connectors (truss ties, straps, hangers, post bases) |  | — | Structure | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
06-310 | 06 | Wood & Rough Carpentry | Nails, screws, adhesives, sill gasket |  | — | Structure | Area |  | 21 | 94.0833 |  |  |  | 1975.75 | SF | 0% | 1975.75 | N | area under roof | Calculated | High
06-320 | 06 | Wood & Rough Carpentry | Framing labor - conditioned (walls, trusses, purlins, sheathing) |  | A101 | Conditioned | Area |  | 21 | 64.1667 |  |  |  | 1347.5 | SF | 0% | 1347.5 | N | 21' x 64.17' | Calculated | High
06-325 | 06 | Wood & Rough Carpentry | Framing labor - porch & carport (beams, posts, trusses, sheathing) |  | A101 | Porch & carport | Area |  | 21 | 29.9167 |  |  |  | 628.25 | SF | 0% | 628.25 | N | 21' x 29.92' | Calculated | High
06-340 | 06 | Wood & Rough Carpentry | Telehandler rental (truss & material set) |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
07-100 | 07 | Thermal & Moisture Protection | Wall insulation R-21 batts (2x6) | R-value ASSUMED | A101 | Conditioned ext. walls | Area | [6 empty] | 1201 | SF | 5% | 1261.05 | N | interior perimeter 166.0 LF x 9' - openings 293 SF | Calculated | High | Verify R-values with energy code (RFI-03).
07-110 | 07 | Thermal & Moisture Protection | Ceiling insulation blown fiberglass R-38 | R-value ASSUMED | A101 RCP | Conditioned ceiling | Area | [6 empty] | 1246.34 | SF | 0% | 1246.34 | N | Σ room ceiling areas (A101 RCP) | Calculated | High
07-115 | 07 | Thermal & Moisture Protection | Air sealing package (top plates, penetrations, rim) |  | — | Envelope | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
07-130 | 07 | Thermal & Moisture Protection | Architectural asphalt shingles, black/charcoal | Design notes | Notes / A401 | Roof 6/12 | Area | [6 empty] | 24.7068 | SQ | 10% | 27.1775 | N | 96.08 x 11.5 x 1.118 x 2 / 100 | Calculated | High | ZIP roof serves as underlayment (Huber listing) - no felt included.
07-140 | 07 | Thermal & Moisture Protection | Hip & ridge cap shingles |  | A401 | Ridge | Length |  | 96.08 |  |  |  |  | 96.08 | LF | 5% | 100.884 | N | ridge length 96.08' | Calculated | High
07-145 | 07 | Thermal & Moisture Protection | Ridge vent (over conditioned attic only) |  | A401 | Ridge | Length |  | 64.17 |  |  |  |  | 64.17 | LF | 0% | 64.17 | N | 64.17' | Assumed | Medium
07-150 | 07 | Thermal & Moisture Protection | Fiber cement smooth panel siding 4x9, incl. Z-flash | Design notes / A401 'Fiber cement smooth panel siding' | A401 | W, E, N elevations + N gable | Area | [6 empty] | 1289.612 | SF | 12% | 1444.3654 | N | 2x70.08x9 + 21x9 + gable 55.13 - (A 120 + B 48 + C 8 + doors 09/10 40) | Calculated | High
07-155 | 07 | Thermal & Moisture Protection | Panel joint trim / battens | A401 joint lines | A401 | Panel siding | Length |  | 200 |  |  |  |  | 200 | LF | 0% | 200 | N | ~16 vertical joints x 9' + horizontals | Assumed | Medium
07-160 | 07 | Thermal & Moisture Protection | Fiber cement T&G siding - porch walls & front gable | Notes: T&G (also says 'lap siding front porch') | A401 Elev B / Notes | Front porch | Area | [6 empty] | 273.626 | SF | 15% | 314.6699 | N | 21x9 - (D 45 + door 01 32) + porch sides 2x5.92x9 + gable 55.13 | Calculated | Medium | Lap vs T&G conflict - RFI-09.
07-170 | 07 | Thermal & Moisture Protection | Fiber cement T&G porch ceiling (sloped) | Design notes | A101 RCP / Notes | Front porch | Area |  | 21 | 5.9167 |  | 1.118 |  | 138.9157 | SF | 15% | 159.7531 | N | 21 x 5.92 x 1.118 slope | Calculated | High
07-180 | 07 | Thermal & Moisture Protection | Fiber cement panel ceiling - covered parking (sloped) | Design notes | A101 RCP / Notes | Covered parking | Area |  | 21 | 24 |  | 1.118 |  | 563.4891 | SF | 12% | 631.1078 | N | 21 x 24 x 1.118 slope | Calculated | High
07-190 | 07 | Thermal & Moisture Protection | Fiber cement vented soffit, 12" | Overhang ASSUMED 12" | A401 | Eaves & rakes | Length |  | 243.6 |  |  |  |  | 243.6 | LF | 10% | 267.96 | N | 2 x 96.08 + 4 x 12.86 | Assumed | Medium
07-200 | 07 | Thermal & Moisture Protection | Fiber cement fascia 5/4x6, painted | A401 | A401 | Eaves & rakes | Length |  | 243.6 |  |  |  |  | 243.6 | LF | 10% | 267.96 | N | 2 x 96.08 + 4 x 12.86 | Calculated | High
07-210 | 07 | Thermal & Moisture Protection | Fiber cement trim 5/4x4 (corners & opening casings) |  | A401 | Exterior | Length |  | 286.67 |  |  |  |  | 286.67 | LF | 10% | 315.337 | N | 6 corners x 9' + opening perimeters (A 100, B 40, C 12, D ganged 28, 01 20, 09/10 32.7) | Calculated | Medium
07-220 | 07 | Thermal & Moisture Protection | 5" seamless aluminum gutters | Shown on A401 | A401 | Both eaves | Length | 2 | 96.08 |  |  |  |  | 192.16 | LF | 0% | 192.16 | N | 2 x 96.08' | Calculated | High
07-225 | 07 | Thermal & Moisture Protection | 2x3 aluminum downspouts w/ splash blocks |  | A401 | Corners | Length | 4 | 10.5 |  |  |  |  | 42 | LF | 0% | 42 | N | 4 x 10.5' | Assumed | Medium
07-230 | 07 | Thermal & Moisture Protection | Drip edge |  | A401 | Eaves & rakes | Length |  | 243.6 |  |  |  |  | 243.6 | LF | 10% | 267.96 | N | eaves + rakes | Calculated | High
07-235 | 07 | Thermal & Moisture Protection | Starter strip |  | A401 | Eaves | Length | 2 | 96.08 |  |  |  |  | 192.16 | LF | 5% | 201.768 | N | 2 x 96.08' | Calculated | High
07-240 | 07 | Thermal & Moisture Protection | Pipe boots, roof flashing & sealant |  | — | Roof | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
07-250 | 07 | Thermal & Moisture Protection | Exterior caulking & sealants |  | — | Exterior | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
08-100 | 08 | Openings | Window Type A - vinyl sliding 6'-0" x 4'-0" | A701 | A701 / A401 Elev D | West wall (hall/kitchen/living) | Count | 5 | [5 empty] | 5 | EA | 0% | 5 | N | schedule = plan = elevation (5) | Measured | High
08-110 | 08 | Openings | Window Type B - vinyl casement 6'-0" x 4'-0" | A701 | A701 / A401 Elev C | Master Bed, Bed #2 | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N | schedule = plan (2) | Measured | High | Egress window - verify clear opening (RFI-10).
08-120 | 08 | Openings | Window Type C - vinyl single hung 2'-0" x 4'-0" | A701 | A701 / A401 Elev A | Laundry | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
08-130 | 08 | Openings | Window Type D - vinyl single hung 3'-0" x 5'-0" (ganged x3, grids) | A701 | A701 / A401 Elev B | Living (porch wall) | Count | 3 | [5 empty] | 3 | EA | 0% | 3 | N |  | Measured | High | Tempered glazing likely near door 01 (RFI-11).
08-200 | 08 | Openings | Door 01 (R1) exterior entry 4'-0" x 8'-0" w/ sidelite, prehung | A701 | A701 | Living / porch | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | Medium | Leaf vs sidelite split not dimensioned (RFI-12).
08-210 | 08 | Openings | Door 09 (R2) exterior 3'-0" x 6'-8" half-lite, prehung | A701 | A701 | Laundry from carport | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
08-220 | 08 | Openings | Door 10 (R5) exterior 3'-0" x 6'-8" flush, prehung | A701 | A701 | Storage from carport | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
08-230 | 08 | Openings | Doors 02/04/05/06/08 (R3) interior 2'-8" x 6'-8" shaker, prehung | A701 | A701 | Interior | Count | 5 | [5 empty] | 5 | EA | 0% | 5 | N |  | Measured | High
08-240 | 08 | Openings | Doors 03/07 (R4) interior bypass 6'-0" x 6'-8" 2-panel | A701 / Notes | A701 | Closets | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
08-250 | 08 | Openings | Hardware - entry handleset & deadbolt (01) |  | A701 | Door 01 | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
08-255 | 08 | Openings | Hardware - exterior keyed lever & deadbolt (09, 10) |  | A701 | Doors 09/10 | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
08-260 | 08 | Openings | Hardware - privacy levers (02, 04, 05, 06) |  | A701 | Bedrooms & baths | Count | 4 | [5 empty] | 4 | EA | 0% | 4 | N |  | Assumed | Medium
08-265 | 08 | Openings | Hardware - passage lever (08) |  | A701 | Laundry | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Assumed | Medium
08-270 | 08 | Openings | Hardware - bypass pulls & track (03, 07) |  | A701 | Closets | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
08-275 | 08 | Openings | Door stops |  | A701 | Swing doors | Count | 8 | [5 empty] | 8 | EA | 0% | 8 | N |  | Calculated | High
09-100 | 09 | Finishes | 1/2" gypsum board - walls, hang & finish Level 3 | Design notes: level 3 (storage level 2) | Notes / A101 | All walls | Area | [6 empty] | 3357.262 | SF | 12% | 3760.1334 | N | ext. walls int. face 166.0x9 - 293 + partitions 138.6x9x2 - int. doors 338 | Calculated | High | Walls taken to 9' in all rooms (8' ceiling rooms slightly over).
09-105 | 09 | Finishes | Moisture-resistant gypsum premium (baths & laundry) |  | A101 | Baths, laundry | Area |  | 955 |  |  |  |  | 955 | SF | 0% | 955 | N | bath #2 275 + master bath 304 + laundry 376 | Calculated | Medium
09-110 | 09 | Finishes | 5/8" gypsum board - ceilings, hang & finish Level 3 |  | A101 RCP | Conditioned ceilings | Area | [6 empty] | 1246.34 | SF | 12% | 1395.9008 | N | Σ room ceiling areas | Calculated | High
09-120 | 09 | Finishes | Drywall accessories (bead, mud, tape, screws) |  | — | Walls & ceilings | Area | [6 empty] | 4603.602 | SF | 0% | 4603.602 | N | walls + ceilings | Calculated | High
09-200 | 09 | Finishes | Baseboard 3-1/4" MDF, painted | Base not specified - ASSUMED | A101 | All rooms | Length | [6 empty] | 352.45 | LF | 10% | 387.695 | N | ext. 166 + partitions 2x138.6 - door openings 60.7 - tubs 10 - cabinets 20 | Assumed | Medium
09-210 | 09 | Finishes | Door casing 2-1/4" MDF, painted | ASSUMED | A701 | Interior doors | Length | [6 empty] | 304.154 | LF | 10% | 334.5694 | N | R3 168.3 + R4 80.7 + ext. doors interior 55.1 | Calculated | Medium
09-220 | 09 | Finishes | Window stool & apron, MDF (drywall returns) | ASSUMED | A701 | Windows | Length | [6 empty] | 115 | LF | 10% | 126.5 | N | 2 x Σ(width + 6"), D ganged | Assumed | Medium
09-230 | 09 | Finishes | Interior paint - walls & ceilings (primer + 2 coats) | Storage not painted (level 2 only) | Notes | Interior | Area | [6 empty] | 4361.202 | SF | 0% | 4361.202 | N | walls + ceilings - storage | Calculated | High
09-240 | 09 | Finishes | Paint interior doors (both faces) |  | A701 | Interior doors | Count | 10 | [5 empty] | 10 | EA | 0% | 10 | N | 5 R3 + 4 R4 panels + 1 (ext. door interior faces avg.) | Calculated | Medium
09-250 | 09 | Finishes | Paint interior trim |  | — | Trim | Length | [6 empty] | 771.604 | LF | 0% | 771.604 | N | base + casing + stool/apron | Calculated | High
09-260 | 09 | Finishes | Exterior paint - fiber cement siding, ceilings, soffit | Primed FC field painted (ASSUMED) | A401 | Exterior | Area | [6 empty] | 2509.2429 | SF | 0% | 2509.2429 | N | panel + T&G + porch ceiling + carport ceiling + soffit | Calculated | Medium
09-265 | 09 | Finishes | Exterior paint - fascia & trim |  | A401 | Exterior | Length | [6 empty] | 730.27 | LF | 0% | 730.27 | N | fascia + trim + joint trim | Calculated | High
09-270 | 09 | Finishes | Exterior doors paint/finish |  | A701 | Doors 01/09/10 | Count | 3 | [5 empty] | 3 | EA | 0% | 3 | N |  | Measured | High
09-280 | 09 | Finishes | Interior caulk & touch-up |  | — | Interior | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
10-100 | 10 | Specialties | Bath accessories (towel bar, ring, TP holder, hook) |  | Notes | Baths | Count | 2 | [5 empty] | 2 | SET | 0% | 2 | N |  | Assumed | Medium
10-110 | 10 | Specialties | Vanity mirrors | Notes: mirror over vanity | Notes | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
10-120 | 10 | Specialties | Closet shelf & rod / laundry & storage shelving | Notes: rod and shelf | Notes / A101 | Closets, laundry, storage | Length |  | 32 |  |  |  |  | 32 | LF | 0% | 32 | N | master closet 10 + bed #2 closet 9.7 + laundry 6 + storage 6 | Measured | Medium
10-130 | 10 | Specialties | Tub shower rods |  | — | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Assumed | Medium
10-140 | 10 | Specialties | House numbers & mailbox |  | — | Exterior | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
11-100 | 11 | Equipment (Appliances) | Appliances (range, refrigerator, OTR microwave, dishwasher, washer/dryer) | Design notes: supplied by owner | Notes | Kitchen, laundry | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | High | Owner furnished - $0 in contract.
11-110 | 11 | Equipment (Appliances) | Appliance installation & hookups (cords, DW, ice maker, OTR vent) |  | Notes | Kitchen, laundry | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
12-100 | 12 | Casework & Countertops | Base cabinets - frameless, shaker doors | Design notes | A101 / Notes | Kitchen run + island | Length | [6 empty] | 11.7 | LF | 0% | 11.7 | N | back run 6.0 + island 7.7 - DW space 2.0 (SCALED) | Measured | Medium
12-110 | 12 | Casework & Countertops | Wall cabinets - frameless, shaker doors | Design notes | A101 / Notes | Kitchen | Length | [6 empty] | 9.4 | LF | 0% | 9.4 | N | flanking range 2.9 + 3.1 + over refrigerator 3.4 (SCALED) | Measured | Medium
12-120 | 12 | Casework & Countertops | Tall pantry cabinet 30" x 24" x 84" |  | A101 | Kitchen | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | Low | Plan symbol at west end of run - verify (RFI-13).
12-125 | 12 | Casework & Countertops | Cabinet fillers, finished ends, island back panel |  | A101 | Kitchen | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
12-130 | 12 | Casework & Countertops | Bath vanities 30" frameless shaker | Design notes | A101 | Bath #2, master bath | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | Medium
12-200 | 12 | Casework & Countertops | Laminate countertops (post-form/custom) | Design notes: laminate | A101 / Notes | Kitchen, island, vanities | Area | [6 empty] | 45.6 | SF | 10% | 50.16 | N | back run 12.75 + island 23.7 + vanities 9.15 | Calculated | Medium
12-210 | 12 | Casework & Countertops | Laminate 4" backsplash |  | A101 | Kitchen, vanities | Length | [6 empty] | 22.52 | LF | 0% | 22.52 | N | kitchen 10.2 + vanities 12.3 | Calculated | Medium
22-100 | 22 | Plumbing | Plumbing rough-in (under-slab DWV, PEX supply, top-out) |  | A101 | 13 connections | Count | 13 | [5 empty] | 13 | EA | 0% | 13 | N | kit. sink, DW, ice, 2 lav, 2 WC, 2 tub, washer, WH, 2 hose bibs | Calculated | Medium
22-110 | 22 | Plumbing | Kitchen sink SS 33" drop-in w/ chrome pull-down faucet | Notes: chrome finish | A101 | Island | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
22-120 | 22 | Plumbing | Lavatory (drop-in) w/ chrome faucet & drain |  | A101 | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
22-130 | 22 | Plumbing | Water closet, elongated 2-pc w/ seat |  | A101 | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
22-140 | 22 | Plumbing | Bathtub 60" w/ chrome tub/shower valve & trim | Notes | A101 | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
22-145 | 22 | Plumbing | Tub surround, 3-pc acrylic | Notes: bathtub surround | Notes | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
22-150 | 22 | Plumbing | Water heater 50 gal electric w/ pan, exp. tank, T&P drain | WH shown in storage (A101) | A101 | Storage | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | Medium | Size/fuel ASSUMED.
22-160 | 22 | Plumbing | Washer box, ice maker box, (2) frost-free hose bibs | Notes: 2 hose bibs | Notes | Laundry, kitchen, exterior | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Measured | High
22-190 | 22 | Plumbing | Fixture trim-out labor |  | — | Fixtures | Count | 7 | [5 empty] | 7 | EA | 0% | 7 | N | sink, 2 lav, 2 WC, 2 tub | Calculated | High
22-195 | 22 | Plumbing | Plumbing permit & inspections |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
23-100 | 23 | HVAC | 2-ton split heat pump w/ air handler & 5 kW heat strip | Notes: 2-ton unit, air handler, ducted | Notes | Attic AH / exterior condenser | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | Medium | Heat pump vs straight-cool + furnace ASSUMED (no gas shown). AH location RFI-14.
23-110 | 23 | HVAC | Duct system (plenum, R-8 flex, registers, returns) |  | A101 | Conditioned | Area |  | 21 | 64.1667 |  |  |  | 1347.5 | SF | 0% | 1347.5 | N | conditioned area | Calculated | High
23-120 | 23 | HVAC | HVAC installation, line set, condensate, pad, thermostat, start-up |  | — | System | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
23-130 | 23 | HVAC | Bath exhaust fans, ducted to exterior | Notes | Notes / A101 RCP | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
23-140 | 23 | HVAC | Dryer vent & wall cap |  | A101 | Laundry | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Assumed | Medium
23-150 | 23 | HVAC | Microwave/range vent duct to exterior | Notes: microwave over stove | Notes | Kitchen | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Assumed | Medium
23-160 | 23 | HVAC | Mechanical permit |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
26-100 | 26 | Electrical | 200A service: meter/main, panel, grounding, surge protection |  | — | Storage / east wall | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Assumed | Medium | Service size ASSUMED (all-electric).
26-110 | 26 | Electrical | Branch rough-in wiring - conditioned (AFCI/GFCI, boxes, wire) |  | A101 | Conditioned | Area |  | 21 | 64.1667 |  |  |  | 1347.5 | SF | 0% | 1347.5 | N | conditioned area | Calculated | High
26-115 | 26 | Electrical | Branch rough-in wiring - porch & carport |  | A101 | Porch & carport | Area |  | 21 | 29.9167 |  |  |  | 628.25 | SF | 0% | 628.25 | N | 21 x 29.92 | Calculated | High
26-120 | 26 | Electrical | Devices: receptacles, switches, GFCI, plates |  | A101 | All rooms | Count | 64 | [5 empty] | 64 | EA | 0% | 64 | N | ~38 receptacles + ~26 switches (code-minimum layout ASSUMED) | Assumed | Low | No electrical plan (RFI-15).
26-130 | 26 | Electrical | Dedicated appliance/equipment circuits |  | — | Range, dryer, WH, HVAC(2), DW, MW, fridge | Count | 8 | [5 empty] | 8 | EA | 0% | 8 | N |  | Calculated | Medium
26-140 | 26 | Electrical | Smoke/CO combination detectors, hardwired, interconnected |  | A101 | Bedrooms, hall, living | Count | 4 | [5 empty] | 4 | EA | 0% | 4 | N |  | Assumed | Medium
26-300 | 26 | Electrical | LED recessed 6" wafer lights | Notes / A101 RCP | A101 RCP | Per RCP | Count | 23 | [5 empty] | 23 | EA | 0% | 23 | N | RCP symbol count (carport 4, laundry, storage, closet, hall 5, baths 4, closet, living 4, porch 2) | Measured | Medium
26-310 | 26 | Electrical | Pendant lights over island | A101 RCP note | A101 RCP | Kitchen island | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
26-320 | 26 | Electrical | Ceiling fans w/ light kit & fan-rated box | Notes | A101 RCP | Master, Bed #2, Living | Count | 3 | [5 empty] | 3 | EA | 0% | 3 | N |  | Measured | High
26-325 | 26 | Electrical | Vanity lights | Notes | Notes | Baths | Count | 2 | [5 empty] | 2 | EA | 0% | 2 | N |  | Measured | High
26-330 | 26 | Electrical | Exterior lights (6 soffit downlights, front door sconce, rear entry light) | Notes: down lighting from soffits | Notes / A401 | Exterior | Count | 8 | [5 empty] | 8 | EA | 0% | 8 | N |  | Assumed | Medium
26-340 | 26 | Electrical | Low-voltage (data/TV 4 drops, doorbell) |  | — | Interior | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
26-350 | 26 | Electrical | Electrical permit |  | — | Project | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Medium
32-100 | 32 | Exterior Improvements | Concrete driveway 4", 12' wide (lot + 10' ROW apron) | A101: 12'-0" drive | A100 / A101 | West side | Area |  | 12 | 129.08 |  |  |  | 1548.96 | SF | 0% | 1548.96 | N | 12' x (24 + 70.08 + 25 front yard + 10 ROW) | Measured | Medium | ROW length ASSUMED 10'; culvert see 32-130.
32-110 | 32 | Exterior Improvements | Concrete apron at covered parking (5' + 4' strips) | A101 | A101 | West of carport | Area |  | 9 | 24 |  |  |  | 216 | SF | 0% | 216 | N | 9' x 24' | Measured | High
32-120 | 32 | Exterior Improvements | Front walk / landing pad | A101 | A101 | Front porch | Area |  | 10.4 | 6 |  |  |  | 62.4 | SF | 0% | 62.4 | N | 10.4' x 6.0' (SCALED) | Measured | Medium
32-130 | 32 | Exterior Improvements | Driveway culvert & headwalls (if open-ditch street) |  | A100 | Street | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Low | RFI-01
32-200 | 32 | Exterior Improvements | Shrubs, 3 gal (planting bed along west wall) | A101 plant symbols | A101 | West bed | Count | 12 | [5 empty] | 12 | EA | 0% | 12 | N |  | Measured | Medium
32-205 | 32 | Exterior Improvements | Bed prep, edging & mulch |  | A101 | 4' x 64.17' bed | Area |  | 4 | 64.17 |  |  |  | 256.68 | SF | 0% | 256.68 | N | 4' x 64.17' | Measured | High
32-207 | 32 | Exterior Improvements | Shade tree, 30 gal | A100/A101 tree symbol | A101 | Front yard | Count | 1 | [5 empty] | 1 | EA | 0% | 1 | N |  | Measured | High
32-210 | 32 | Exterior Improvements | Sod - front & east side yards |  | A100 | Front/side | Area |  | 1700 |  |  |  |  | 1700 | SF | 0% | 1700 | N | front ~950 + east side 8' x 94' ~750 | Assumed | Medium
32-215 | 32 | Exterior Improvements | Seed & straw - balance of disturbed lot |  | A100 | Rear | Area | [6 empty] | 3360.16 | SF | 0% | 3360.16 | N | lot 9,000 - slab - paving (in lot) - bed - sod | Calculated | Medium
33-100 | 33 | Utilities | Water service 1" (meter to house) |  | A100 | Front | Length |  | 45 |  |  |  |  | 45 | LF | 0% | 45 | N |  | Assumed | Low | Meter location unknown (RFI-01).
33-110 | 33 | Utilities | Sewer service 4" PVC w/ cleanouts |  | A100 | Front | Length |  | 50 |  |  |  |  | 50 | LF | 0% | 50 | N |  | Assumed | Low
33-120 | 33 | Utilities | Water/sewer tap, meter & impact fees (municipal) |  | — | Utility | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Low | Septic system EXCLUDED - assumes public sewer available.
33-130 | 33 | Utilities | Underground electric service lateral |  | A100 | Site | Length |  | 60 |  |  |  |  | 60 | LF | 0% | 60 | N |  | Assumed | Low
33-140 | 33 | Utilities | Utility company service/connection charges |  | — | Utility | Allowance | 1 | [5 empty] | 1 | LS | 0% | 1 | N |  | Allowance | Low

## Cost Database
Cost ID | Cost Code | Description | Unit | Material $/unit | Labor $/unit | Sub / Equip / Other $/unit | Total $/unit | Source | Market | Price Date | Notes
01-100 | 01 | Building permit & plan review | LS | 0 | 0 | 2600 | 2600 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-105 | 01 | Engineering: foundation design, carport/porch beams, truss review | LS | 0 | 0 | 1800 | 1800 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-106 | 01 | Geotechnical investigation (borings, PI, slab recommendations) | LS | 0 | 0 | 1900 | 1900 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-110 | 01 | Survey: boundary, staking, form-board, final as-built | LS | 0 | 0 | 1850 | 1850 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-120 | 01 | Temporary power pole, connection & usage | LS | 250 | 0 | 900 | 1150 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-125 | 01 | Temporary water & usage | LS | 0 | 0 | 300 | 300 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-130 | 01 | Portable toilet | MO | 0 | 0 | 165 | 165 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-140 | 01 | Dumpster, 20 CY, haul & dump | EA | 0 | 0 | 485 | 485 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-150 | 01 | Builder's risk insurance | LS | 0 | 0 | 1250 | 1250 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-160 | 01 | Site supervision (part-time superintendent) | WK | 0 | 650 | 0 | 650 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-170 | 01 | Final construction clean incl. windows | SF | 0 | 0 | 0.35 | 0.35 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-175 | 01 | Periodic jobsite cleanup | LS | 0 | 900 | 0 | 900 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-180 | 01 | Finished-slab protection (Ram Board/taped) - smooth trowel floors | SF | 0.38 | 0.08 | 0 | 0.46 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-190 | 01 | Termite pre-treatment & LDAF certificate | LS | 0 | 0 | 525 | 525 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-200 | 01 | Small tools & consumables | LS | 600 | 0 | 0 | 600 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
01-210 | 01 | Energy code testing (blower door / duct leakage) | LS | 0 | 0 | 450 | 450 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
31-100 | 31 | Clear & grub, strip topsoil (building & drive area) | LS | 0 | 0 | 2800 | 2800 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
31-120 | 31 | Select fill building pad, 12" avg, compacted (loose CY incl. 25% shrink) | CY | 18 | 0 | 7.5 | 25.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
31-130 | 31 | Fine grade building pad | SF | 0 | 0 | 0.18 | 0.18 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
31-140 | 31 | Final grading & topsoil spread | LS | 0 | 0 | 1800 | 1800 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
31-150 | 31 | Silt fence / erosion control | LF | 0.9 | 1.6 | 0 | 2.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-100 | 03 | Slab-on-grade 4" (house, porch, carport) - concrete | CY | 168 | 0 | 0 | 168 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-110 | 03 | Perimeter grade beam 12" w x 20" below slab - concrete | CY | 168 | 0 | 0 | 168 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-120 | 03 | Interior grade beams 12" w x 16" below slab - concrete | CY | 168 | 0 | 0 | 168 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-130 | 03 | Vapor retarder 10 mil poly, lapped & taped | SF | 0.11 | 0.06 | 0 | 0.17 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-140 | 03 | Rebar #5 continuous in grade beams (4 bars) | LF | 0.85 | 0.35 | 0 | 1.2 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-150 | 03 | Rebar #3 @ 18" O.C. each way in slab | LF | 0.32 | 0.18 | 0 | 0.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-160 | 03 | Forms, chairs, stakes, ties, edge/expansion material | SF | 0.22 | 0 | 0 | 0.22 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-170 | 03 | Foundation labor: form, set steel, place & finish (sub) | SF | 0 | 3 | 0 | 3 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-175 | 03 | Concrete pump truck | LS | 0 | 0 | 1150 | 1150 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-180 | 03 | Finished concrete floors: smooth trowel premium, grind, densifier & sealer | SF | 0 | 0 | 2.4 | 2.4 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-185 | 03 | Porch slab: smooth trowel, slope away, sealer | SF | 0.35 | 0.4 | 0 | 0.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-190 | 03 | Anchor bolts / sill anchors at exterior walls | EA | 2.75 | 1.5 | 0 | 4.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-200 | 03 | Saw-cut control joints | LF | 0 | 0 | 1.75 | 1.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
03-220 | 03 | Carport post footings 24"x24"x24" w/ post base | EA | 55 | 0 | 240 | 295 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-100 | 06 | PT 2x6 bottom/sill plate - exterior walls | LF | 1.15 | 0 | 0 | 1.15 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-110 | 06 | 2x6 double top plate - exterior walls | LF | 0.95 | 0 | 0 | 0.95 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-120 | 06 | 2x6 x 104-5/8" studs @ 24" O.C. - exterior walls | EA | 9.25 | 0 | 0 | 9.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-130 | 06 | 2x10 header stock, 2-ply - exterior openings | LF | 1.75 | 0 | 0 | 1.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-140 | 06 | PT 2x4 bottom plate - interior partitions | LF | 0.8 | 0 | 0 | 0.8 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-150 | 06 | 2x4 double top plate - interior partitions | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-160 | 06 | 2x4 x 104-5/8" studs @ 24" O.C. - partitions | EA | 5.75 | 0 | 0 | 5.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-170 | 06 | Interior door headers / misc 2x6 | LF | 0.95 | 0 | 0 | 0.95 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-180 | 06 | Blocking & backing (cabinets, tubs, accessories, TV, grab-bar ready) | LF | 0.95 | 0 | 0 | 0.95 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-190 | 06 | Roof trusses - common 6/12, 21' span, flat bottom chord @ 4' O.C. | EA | 205 | 0 | 0 | 205 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-191 | 06 | Roof trusses - vaulted (parallel-chord) 6/12 for sloped carport/porch ceilings | EA | 275 | 0 | 0 | 275 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-192 | 06 | End trusses at open gables (vaulted, w/ rake outlookers) | EA | 300 | 0 | 0 | 300 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-200 | 06 | 2x4 roof purlins @ 24" O.C. (flat) over 48" trusses | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-210 | 06 | 2x4 ceiling furring @ 24" O.C. under trusses (conditioned) | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-215 | 06 | 2x4 ceiling joists & ledgers for 8' ceilings | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-220 | 06 | 2x4 nailers for sloped carport & porch ceilings | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-230 | 06 | Truss permanent lateral & diagonal bracing | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-240 | 06 | 2x6 sub-fascia | LF | 0.95 | 0 | 0 | 0.95 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-245 | 06 | 2x4 soffit framing / lookouts | LF | 0.62 | 0 | 0 | 0.62 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-250 | 06 | LVL beams 3-1/2" x 14" (carport eaves 2 x 25', porch front 22') | LF | 34 | 0 | 0 | 34 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-260 | 06 | 6x6 PT posts w/ base & cap, wrapped | EA | 150 | 0 | 0 | 150 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-270 | 06 | ZIP System 7/16" wall sheathing, 4x9 panels | SHT | 45 | 0 | 0 | 45 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-280 | 06 | ZIP System 5/8" roof sheathing, 4x8 panels | SHT | 52 | 0 | 0 | 52 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-290 | 06 | ZIP System tape 3.75" x 90' rolls | RL | 36 | 0 | 0 | 36 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-295 | 06 | ZIP liquid flash / stretch tape at openings & penetrations | LS | 350 | 0 | 0 | 350 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-300 | 06 | Structural connectors (truss ties, straps, hangers, post bases) | LS | 1150 | 0 | 0 | 1150 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-310 | 06 | Nails, screws, adhesives, sill gasket | SF | 0.45 | 0 | 0 | 0.45 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-320 | 06 | Framing labor - conditioned (walls, trusses, purlins, sheathing) | SF | 0 | 7.25 | 0 | 7.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-325 | 06 | Framing labor - porch & carport (beams, posts, trusses, sheathing) | SF | 0 | 3.75 | 0 | 3.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
06-340 | 06 | Telehandler rental (truss & material set) | LS | 0 | 0 | 1150 | 1150 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-100 | 07 | Wall insulation R-21 batts (2x6) | SF | 0 | 0 | 1.15 | 1.15 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-110 | 07 | Ceiling insulation blown fiberglass R-38 | SF | 0 | 0 | 1.45 | 1.45 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-115 | 07 | Air sealing package (top plates, penetrations, rim) | LS | 0 | 0 | 650 | 650 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-130 | 07 | Architectural asphalt shingles, black/charcoal | SQ | 118 | 92 | 0 | 210 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-140 | 07 | Hip & ridge cap shingles | LF | 3.25 | 1.25 | 0 | 4.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-145 | 07 | Ridge vent (over conditioned attic only) | LF | 3.75 | 1.5 | 0 | 5.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-150 | 07 | Fiber cement smooth panel siding 4x9, incl. Z-flash | SF | 2.15 | 2.35 | 0 | 4.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-155 | 07 | Panel joint trim / battens | LF | 1.1 | 1.25 | 0 | 2.35 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-160 | 07 | Fiber cement T&G siding - porch walls & front gable | SF | 2.85 | 2.75 | 0 | 5.6 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-170 | 07 | Fiber cement T&G porch ceiling (sloped) | SF | 3.1 | 3.25 | 0 | 6.35 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-180 | 07 | Fiber cement panel ceiling - covered parking (sloped) | SF | 2.15 | 2.6 | 0 | 4.75 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-190 | 07 | Fiber cement vented soffit, 12" | LF | 3.25 | 3 | 0 | 6.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-200 | 07 | Fiber cement fascia 5/4x6, painted | LF | 2.4 | 2.1 | 0 | 4.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-210 | 07 | Fiber cement trim 5/4x4 (corners & opening casings) | LF | 1.75 | 2.1 | 0 | 3.85 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-220 | 07 | 5" seamless aluminum gutters | LF | 0 | 0 | 8.5 | 8.5 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-225 | 07 | 2x3 aluminum downspouts w/ splash blocks | LF | 0 | 0 | 8 | 8 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-230 | 07 | Drip edge | LF | 0.85 | 0.4 | 0 | 1.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-235 | 07 | Starter strip | LF | 0.75 | 0.25 | 0 | 1 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-240 | 07 | Pipe boots, roof flashing & sealant | LS | 225 | 150 | 0 | 375 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
07-250 | 07 | Exterior caulking & sealants | LS | 450 | 500 | 0 | 950 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-100 | 08 | Window Type A - vinyl sliding 6'-0" x 4'-0" | EA | 420 | 95 | 0 | 515 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-110 | 08 | Window Type B - vinyl casement 6'-0" x 4'-0" | EA | 925 | 110 | 0 | 1035 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-120 | 08 | Window Type C - vinyl single hung 2'-0" x 4'-0" | EA | 215 | 85 | 0 | 300 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-130 | 08 | Window Type D - vinyl single hung 3'-0" x 5'-0" (ganged x3, grids) | EA | 335 | 95 | 0 | 430 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-200 | 08 | Door 01 (R1) exterior entry 4'-0" x 8'-0" w/ sidelite, prehung | EA | 1950 | 275 | 0 | 2225 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-210 | 08 | Door 09 (R2) exterior 3'-0" x 6'-8" half-lite, prehung | EA | 520 | 185 | 0 | 705 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-220 | 08 | Door 10 (R5) exterior 3'-0" x 6'-8" flush, prehung | EA | 365 | 185 | 0 | 550 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-230 | 08 | Doors 02/04/05/06/08 (R3) interior 2'-8" x 6'-8" shaker, prehung | EA | 195 | 95 | 0 | 290 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-240 | 08 | Doors 03/07 (R4) interior bypass 6'-0" x 6'-8" 2-panel | EA | 395 | 145 | 0 | 540 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-250 | 08 | Hardware - entry handleset & deadbolt (01) | EA | 215 | 45 | 0 | 260 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-255 | 08 | Hardware - exterior keyed lever & deadbolt (09, 10) | EA | 95 | 40 | 0 | 135 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-260 | 08 | Hardware - privacy levers (02, 04, 05, 06) | EA | 32 | 20 | 0 | 52 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-265 | 08 | Hardware - passage lever (08) | EA | 28 | 20 | 0 | 48 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-270 | 08 | Hardware - bypass pulls & track (03, 07) | EA | 22 | 10 | 0 | 32 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
08-275 | 08 | Door stops | EA | 5 | 4 | 0 | 9 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-100 | 09 | 1/2" gypsum board - walls, hang & finish Level 3 | SF | 0.58 | 1.55 | 0 | 2.13 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-105 | 09 | Moisture-resistant gypsum premium (baths & laundry) | SF | 0.18 | 0 | 0 | 0.18 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-110 | 09 | 5/8" gypsum board - ceilings, hang & finish Level 3 | SF | 0.72 | 1.75 | 0 | 2.47 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-120 | 09 | Drywall accessories (bead, mud, tape, screws) | SF | 0.12 | 0 | 0 | 0.12 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-200 | 09 | Baseboard 3-1/4" MDF, painted | LF | 1.1 | 1.35 | 0 | 2.45 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-210 | 09 | Door casing 2-1/4" MDF, painted | LF | 0.85 | 1.25 | 0 | 2.1 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-220 | 09 | Window stool & apron, MDF (drywall returns) | LF | 1.6 | 2.5 | 0 | 4.1 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-230 | 09 | Interior paint - walls & ceilings (primer + 2 coats) | SF | 0.28 | 1.02 | 0 | 1.3 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-240 | 09 | Paint interior doors (both faces) | EA | 18 | 65 | 0 | 83 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-250 | 09 | Paint interior trim | LF | 0.1 | 0.75 | 0 | 0.85 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-260 | 09 | Exterior paint - fiber cement siding, ceilings, soffit | SF | 0.32 | 0.95 | 0 | 1.27 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-265 | 09 | Exterior paint - fascia & trim | LF | 0.08 | 0.65 | 0 | 0.73 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-270 | 09 | Exterior doors paint/finish | EA | 25 | 85 | 0 | 110 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
09-280 | 09 | Interior caulk & touch-up | LS | 150 | 250 | 0 | 400 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
10-100 | 10 | Bath accessories (towel bar, ring, TP holder, hook) | SET | 140 | 85 | 0 | 225 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
10-110 | 10 | Vanity mirrors | EA | 95 | 45 | 0 | 140 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
10-120 | 10 | Closet shelf & rod / laundry & storage shelving | LF | 9 | 7 | 0 | 16 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
10-130 | 10 | Tub shower rods | EA | 30 | 20 | 0 | 50 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
10-140 | 10 | House numbers & mailbox | LS | 175 | 75 | 0 | 250 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
11-100 | 11 | Appliances (range, refrigerator, OTR microwave, dishwasher, washer/dryer) | LS | 0 | 0 | 0 | 0 | Owner furnished per design notes | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
11-110 | 11 | Appliance installation & hookups (cords, DW, ice maker, OTR vent) | LS | 85 | 350 | 0 | 435 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-100 | 12 | Base cabinets - frameless, shaker doors | LF | 285 | 45 | 0 | 330 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-110 | 12 | Wall cabinets - frameless, shaker doors | LF | 215 | 40 | 0 | 255 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-120 | 12 | Tall pantry cabinet 30" x 24" x 84" | EA | 875 | 85 | 0 | 960 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-125 | 12 | Cabinet fillers, finished ends, island back panel | LS | 350 | 100 | 0 | 450 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-130 | 12 | Bath vanities 30" frameless shaker | EA | 425 | 85 | 0 | 510 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-200 | 12 | Laminate countertops (post-form/custom) | SF | 22 | 9 | 0 | 31 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
12-210 | 12 | Laminate 4" backsplash | LF | 6 | 3 | 0 | 9 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-100 | 22 | Plumbing rough-in (under-slab DWV, PEX supply, top-out) | EA | 220 | 480 | 0 | 700 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-110 | 22 | Kitchen sink SS 33" drop-in w/ chrome pull-down faucet | EA | 425 | 0 | 0 | 425 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-120 | 22 | Lavatory (drop-in) w/ chrome faucet & drain | EA | 195 | 0 | 0 | 195 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-130 | 22 | Water closet, elongated 2-pc w/ seat | EA | 285 | 0 | 0 | 285 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-140 | 22 | Bathtub 60" w/ chrome tub/shower valve & trim | EA | 520 | 150 | 0 | 670 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-145 | 22 | Tub surround, 3-pc acrylic | EA | 375 | 225 | 0 | 600 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-150 | 22 | Water heater 50 gal electric w/ pan, exp. tank, T&P drain | EA | 925 | 350 | 0 | 1275 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-160 | 22 | Washer box, ice maker box, (2) frost-free hose bibs | LS | 190 | 0 | 0 | 190 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-190 | 22 | Fixture trim-out labor | EA | 0 | 145 | 0 | 145 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
22-195 | 22 | Plumbing permit & inspections | LS | 0 | 0 | 275 | 275 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-100 | 23 | 2-ton split heat pump w/ air handler & 5 kW heat strip | EA | 4650 | 0 | 0 | 4650 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-110 | 23 | Duct system (plenum, R-8 flex, registers, returns) | SF | 1.35 | 1.1 | 0 | 2.45 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-120 | 23 | HVAC installation, line set, condensate, pad, thermostat, start-up | LS | 650 | 2600 | 0 | 3250 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-130 | 23 | Bath exhaust fans, ducted to exterior | EA | 95 | 125 | 0 | 220 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-140 | 23 | Dryer vent & wall cap | EA | 55 | 110 | 0 | 165 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-150 | 23 | Microwave/range vent duct to exterior | EA | 65 | 125 | 0 | 190 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
23-160 | 23 | Mechanical permit | LS | 0 | 0 | 175 | 175 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-100 | 26 | 200A service: meter/main, panel, grounding, surge protection | LS | 1750 | 1250 | 0 | 3000 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-110 | 26 | Branch rough-in wiring - conditioned (AFCI/GFCI, boxes, wire) | SF | 1.55 | 2.1 | 0 | 3.65 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-115 | 26 | Branch rough-in wiring - porch & carport | SF | 0.45 | 0.65 | 0 | 1.1 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-120 | 26 | Devices: receptacles, switches, GFCI, plates | EA | 7 | 18 | 0 | 25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-130 | 26 | Dedicated appliance/equipment circuits | EA | 95 | 125 | 0 | 220 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-140 | 26 | Smoke/CO combination detectors, hardwired, interconnected | EA | 48 | 30 | 0 | 78 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-300 | 26 | LED recessed 6" wafer lights | EA | 24 | 40 | 0 | 64 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-310 | 26 | Pendant lights over island | EA | 120 | 55 | 0 | 175 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-320 | 26 | Ceiling fans w/ light kit & fan-rated box | EA | 175 | 85 | 0 | 260 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-325 | 26 | Vanity lights | EA | 85 | 45 | 0 | 130 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-330 | 26 | Exterior lights (6 soffit downlights, front door sconce, rear entry light) | EA | 55 | 50 | 0 | 105 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-340 | 26 | Low-voltage (data/TV 4 drops, doorbell) | LS | 225 | 375 | 0 | 600 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
26-350 | 26 | Electrical permit | LS | 0 | 0 | 225 | 225 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-100 | 32 | Concrete driveway 4", 12' wide (lot + 10' ROW apron) | SF | 3.35 | 3.9 | 0 | 7.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-110 | 32 | Concrete apron at covered parking (5' + 4' strips) | SF | 3.35 | 3.9 | 0 | 7.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-120 | 32 | Front walk / landing pad | SF | 3.35 | 3.9 | 0 | 7.25 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-130 | 32 | Driveway culvert & headwalls (if open-ditch street) | LS | 0 | 0 | 1200 | 1200 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-200 | 32 | Shrubs, 3 gal (planting bed along west wall) | EA | 28 | 15 | 0 | 43 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-205 | 32 | Bed prep, edging & mulch | SF | 0.55 | 0.45 | 0 | 1 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-207 | 32 | Shade tree, 30 gal | EA | 275 | 125 | 0 | 400 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-210 | 32 | Sod - front & east side yards | SF | 0.55 | 0.3 | 0 | 0.85 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
32-215 | 32 | Seed & straw - balance of disturbed lot | SF | 0.08 | 0.06 | 0 | 0.14 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
33-100 | 33 | Water service 1" (meter to house) | LF | 0 | 0 | 14 | 14 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
33-110 | 33 | Sewer service 4" PVC w/ cleanouts | LF | 0 | 0 | 26 | 26 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
33-120 | 33 | Water/sewer tap, meter & impact fees (municipal) | LS | 0 | 0 | 3500 | 3500 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
33-130 | 33 | Underground electric service lateral | LF | 0 | 0 | 16 | 16 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax
33-140 | 33 | Utility company service/connection charges | LS | 0 | 0 | 800 | 800 | Estimator budget unit cost, NE Louisiana (Monroe/Ouachita) Q4-2026 - not a quote; verify with local supplier/sub | Monroe / West Monroe / Ouachita Parish, LA | 2026-10-15 | Material pre-tax

## Estimate Detail
Line | Cost Code | Division | Description | Takeoff ID | Qty (gross) | Unit | Cost ID | Material $/u | Labor $/u | Sub/Equip $/u | Material $ | Labor $ | Sub/Equip $ | Line Total $ | Basis | Confidence | $ / Cond. SF
1 | 01 | General Requirements | Building permit & plan review | 01-100 | 1 | LS | 01-100 | 0 | 0 | 2600 | 0 | 0 | 2600 | 2600 | Allowance | Medium | 1.9231
2 | 01 | General Requirements | Engineering: foundation design, carport/porch beams, truss review | 01-105 | 1 | LS | 01-105 | 0 | 0 | 1800 | 0 | 0 | 1800 | 1800 | Allowance | Medium | 1.3314
3 | 01 | General Requirements | Geotechnical investigation (borings, PI, slab recommendations) | 01-106 | 1 | LS | 01-106 | 0 | 0 | 1900 | 0 | 0 | 1900 | 1900 | Allowance | Medium | 1.4053
4 | 01 | General Requirements | Survey: boundary, staking, form-board, final as-built | 01-110 | 1 | LS | 01-110 | 0 | 0 | 1850 | 0 | 0 | 1850 | 1850 | Allowance | Medium | 1.3683
5 | 01 | General Requirements | Temporary power pole, connection & usage | 01-120 | 1 | LS | 01-120 | 250 | 0 | 900 | 250 | 0 | 900 | 1150 | Allowance | Medium | 0.85059
6 | 01 | General Requirements | Temporary water & usage | 01-125 | 1 | LS | 01-125 | 0 | 0 | 300 | 0 | 0 | 300 | 300 | Allowance | Medium | 0.22189
7 | 01 | General Requirements | Portable toilet | 01-130 | 5 | MO | 01-130 | 0 | 0 | 165 | 0 | 0 | 825 | 825 | Assumed | Medium | 0.61021
8 | 01 | General Requirements | Dumpster, 20 CY, haul & dump | 01-140 | 5 | EA | 01-140 | 0 | 0 | 485 | 0 | 0 | 2425 | 2425 | Assumed | Medium | 1.7936
9 | 01 | General Requirements | Builder's risk insurance | 01-150 | 1 | LS | 01-150 | 0 | 0 | 1250 | 0 | 0 | 1250 | 1250 | Allowance | Medium | 0.92456
10 | 01 | General Requirements | Site supervision (part-time superintendent) | 01-160 | 20 | WK | 01-160 | 0 | 650 | 0 | 0 | 13000 | 0 | 13000 | Assumed | Medium | 9.6154
11 | 01 | General Requirements | Final construction clean incl. windows | 01-170 | 1975.75 | SF | 01-170 | 0 | 0 | 0.35 | 0 | 0 | 691.5125 | 691.5125 | Calculated | High | 0.51147
12 | 01 | General Requirements | Periodic jobsite cleanup | 01-175 | 1 | LS | 01-175 | 0 | 900 | 0 | 0 | 900 | 0 | 900 | Allowance | Medium | 0.66568
13 | 01 | General Requirements | Finished-slab protection (Ram Board/taped) - smooth trowel floors | 01-180 | 1482.25 | SF | 01-180 | 0.38 | 0.08 | 0 | 563.255 | 118.58 | 0 | 681.835 | Calculated | High | 0.50432
14 | 01 | General Requirements | Termite pre-treatment & LDAF certificate | 01-190 | 1 | LS | 01-190 | 0 | 0 | 525 | 0 | 0 | 525 | 525 | Allowance | Medium | 0.38831
15 | 01 | General Requirements | Small tools & consumables | 01-200 | 1 | LS | 01-200 | 600 | 0 | 0 | 600 | 0 | 0 | 600 | Allowance | Medium | 0.44379
16 | 01 | General Requirements | Energy code testing (blower door / duct leakage) | 01-210 | 1 | LS | 01-210 | 0 | 0 | 450 | 0 | 0 | 450 | 450 | Allowance | Medium | 0.33284
17 | 31 | Earthwork | Clear & grub, strip topsoil (building & drive area) | 31-100 | 1 | LS | 31-100 | 0 | 0 | 2800 | 0 | 0 | 2800 | 2800 | Allowance | Low | 2.071
18 | 31 | Earthwork | Select fill building pad, 12" avg, compacted (loose CY incl. 25% shrink) | 31-120 | 150 | CY | 31-120 | 18 | 0 | 7.5 | 2700 | 0 | 1125 | 3825 | Assumed | Low | 2.8291
19 | 31 | Earthwork | Fine grade building pad | 31-130 | 3226.5833 | SF | 31-130 | 0 | 0 | 0.18 | 0 | 0 | 580.785 | 580.785 | Calculated | High | 0.42957
20 | 31 | Earthwork | Final grading & topsoil spread | 31-140 | 1 | LS | 31-140 | 0 | 0 | 1800 | 0 | 0 | 1800 | 1800 | Allowance | Medium | 1.3314
21 | 31 | Earthwork | Silt fence / erosion control | 31-150 | 230 | LF | 31-150 | 0.9 | 1.6 | 0 | 207 | 368 | 0 | 575 | Assumed | Medium | 0.4253
22 | 03 | Concrete | Slab-on-grade 4" (house, porch, carport) - concrete | 03-100 | 25.6116 | CY | 03-100 | 168 | 0 | 0 | 4302.7444 | 0 | 0 | 4302.7444 | Calculated | High | 3.1825
23 | 03 | Concrete | Perimeter grade beam 12" w x 20" below slab - concrete | 03-110 | 15.3444 | CY | 03-110 | 168 | 0 | 0 | 2577.8667 | 0 | 0 | 2577.8667 | Assumed | Medium | 1.9067
24 | 03 | Concrete | Interior grade beams 12" w x 16" below slab - concrete | 03-120 | 9.9778 | CY | 03-120 | 168 | 0 | 0 | 1676.2667 | 0 | 0 | 1676.2667 | Assumed | Low | 1.2398
25 | 03 | Concrete | Vapor retarder 10 mil poly, lapped & taped | 03-130 | 2272.1125 | SF | 03-130 | 0.11 | 0.06 | 0 | 249.9324 | 136.3268 | 0 | 386.2591 | Calculated | High | 0.28569
26 | 03 | Concrete | Rebar #5 continuous in grade beams (4 bars) | 03-140 | 1835.9 | LF | 03-140 | 0.85 | 0.35 | 0 | 1560.515 | 642.565 | 0 | 2203.08 | Assumed | Medium | 1.6295
27 | 03 | Concrete | Rebar #3 @ 18" O.C. each way in slab | 03-150 | 2897.7667 | LF | 03-150 | 0.32 | 0.18 | 0 | 927.2853 | 521.598 | 0 | 1448.8833 | Assumed | Medium | 1.0717
28 | 03 | Concrete | Forms, chairs, stakes, ties, edge/expansion material | 03-160 | 1975.75 | SF | 03-160 | 0.22 | 0 | 0 | 434.665 | 0 | 0 | 434.665 | Calculated | High | 0.3215
29 | 03 | Concrete | Foundation labor: form, set steel, place & finish (sub) | 03-170 | 1975.75 | SF | 03-170 | 0 | 3 | 0 | 0 | 5927.25 | 0 | 5927.25 | Calculated | High | 4.3841
30 | 03 | Concrete | Concrete pump truck | 03-175 | 1 | LS | 03-175 | 0 | 0 | 1150 | 0 | 0 | 1150 | 1150 | Allowance | Medium | 0.85059
31 | 03 | Concrete | Finished concrete floors: smooth trowel premium, grind, densifier & sealer | 03-180 | 1347.5 | SF | 03-180 | 0 | 0 | 2.4 | 0 | 0 | 3234 | 3234 | Calculated | High | 2.392
32 | 03 | Concrete | Porch slab: smooth trowel, slope away, sealer | 03-185 | 124.25 | SF | 03-185 | 0.35 | 0.4 | 0 | 43.4875 | 49.7 | 0 | 93.1875 | Calculated | High | 0.068926
33 | 03 | Concrete | Anchor bolts / sill anchors at exterior walls | 03-190 | 46 | EA | 03-190 | 2.75 | 1.5 | 0 | 126.5 | 69 | 0 | 195.5 | Calculated | Medium | 0.1446
34 | 03 | Concrete | Saw-cut control joints | 03-200 | 120 | LF | 03-200 | 0 | 0 | 1.75 | 0 | 0 | 210 | 210 | Assumed | Medium | 0.15533
35 | 03 | Concrete | Carport post footings 24"x24"x24" w/ post base | 03-220 | 2 | EA | 03-220 | 55 | 0 | 240 | 110 | 0 | 480 | 590 | Measured | Medium | 0.43639
36 | 06 | Wood & Rough Carpentry | PT 2x6 bottom/sill plate - exterior walls | 06-100 | 200.387 | LF | 06-100 | 1.15 | 0 | 0 | 230.4451 | 0 | 0 | 230.4451 | Calculated | High | 0.17045
37 | 06 | Wood & Rough Carpentry | 2x6 double top plate - exterior walls | 06-110 | 400.774 | LF | 06-110 | 0.95 | 0 | 0 | 380.7353 | 0 | 0 | 380.7353 | Calculated | High | 0.28161
38 | 06 | Wood & Rough Carpentry | 2x6 x 104-5/8" studs @ 24" O.C. - exterior walls | 06-120 | 229 | EA | 06-120 | 9.25 | 0 | 0 | 2118.25 | 0 | 0 | 2118.25 | Calculated | Medium | 1.5668
39 | 06 | Wood & Rough Carpentry | 2x10 header stock, 2-ply - exterior openings | 06-130 | 151.8 | LF | 06-130 | 1.75 | 0 | 0 | 265.65 | 0 | 0 | 265.65 | Calculated | Medium | 0.19649
40 | 06 | Wood & Rough Carpentry | PT 2x4 bottom plate - interior partitions | 06-140 | 152.416 | LF | 06-140 | 0.8 | 0 | 0 | 121.9328 | 0 | 0 | 121.9328 | Measured | Medium | 0.090187
41 | 06 | Wood & Rough Carpentry | 2x4 double top plate - interior partitions | 06-150 | 304.832 | LF | 06-150 | 0.62 | 0 | 0 | 188.9958 | 0 | 0 | 188.9958 | Calculated | High | 0.13979
42 | 06 | Wood & Rough Carpentry | 2x4 x 104-5/8" studs @ 24" O.C. - partitions | 06-160 | 157 | EA | 06-160 | 5.75 | 0 | 0 | 902.75 | 0 | 0 | 902.75 | Calculated | Medium | 0.66771
43 | 06 | Wood & Rough Carpentry | Interior door headers / misc 2x6 | 06-170 | 60 | LF | 06-170 | 0.95 | 0 | 0 | 57 | 0 | 0 | 57 | Assumed | Medium | 0.04216
44 | 06 | Wood & Rough Carpentry | Blocking & backing (cabinets, tubs, accessories, TV, grab-bar ready) | 06-180 | 250 | LF | 06-180 | 0.95 | 0 | 0 | 237.5 | 0 | 0 | 237.5 | Allowance | Medium | 0.17567
45 | 06 | Wood & Rough Carpentry | Roof trusses - common 6/12, 21' span, flat bottom chord @ 4' O.C. | 06-190 | 17 | EA | 06-190 | 205 | 0 | 0 | 3485 | 0 | 0 | 3485 | Calculated | Medium | 2.5777
46 | 06 | Wood & Rough Carpentry | Roof trusses - vaulted (parallel-chord) 6/12 for sloped carport/porch ceilings | 06-191 | 6 | EA | 06-191 | 275 | 0 | 0 | 1650 | 0 | 0 | 1650 | Calculated | Medium | 1.2204
47 | 06 | Wood & Rough Carpentry | End trusses at open gables (vaulted, w/ rake outlookers) | 06-192 | 2 | EA | 06-192 | 300 | 0 | 0 | 600 | 0 | 0 | 600 | Calculated | Medium | 0.44379
48 | 06 | Wood & Rough Carpentry | 2x4 roof purlins @ 24" O.C. (flat) over 48" trusses | 06-200 | 1479.632 | LF | 06-200 | 0.62 | 0 | 0 | 917.3718 | 0 | 0 | 917.3718 | Assumed | Low | 0.67853
49 | 06 | Wood & Rough Carpentry | 2x4 ceiling furring @ 24" O.C. under trusses (conditioned) | 06-210 | 693.88 | LF | 06-210 | 0.62 | 0 | 0 | 430.2056 | 0 | 0 | 430.2056 | Assumed | Medium | 0.3182
50 | 06 | Wood & Rough Carpentry | 2x4 ceiling joists & ledgers for 8' ceilings | 06-215 | 169.334 | LF | 06-215 | 0.62 | 0 | 0 | 104.9871 | 0 | 0 | 104.9871 | Calculated | Medium | 0.077653
51 | 06 | Wood & Rough Carpentry | 2x4 nailers for sloped carport & porch ceilings | 06-220 | 427.856 | LF | 06-220 | 0.62 | 0 | 0 | 265.2707 | 0 | 0 | 265.2707 | Assumed | Medium | 0.19621
52 | 06 | Wood & Rough Carpentry | Truss permanent lateral & diagonal bracing | 06-230 | 400 | LF | 06-230 | 0.62 | 0 | 0 | 248 | 0 | 0 | 248 | Allowance | Medium | 0.18343
53 | 06 | Wood & Rough Carpentry | 2x6 sub-fascia | 06-240 | 267.96 | LF | 06-240 | 0.95 | 0 | 0 | 254.562 | 0 | 0 | 254.562 | Calculated | High | 0.18829
54 | 06 | Wood & Rough Carpentry | 2x4 soffit framing / lookouts | 06-245 | 200 | LF | 06-245 | 0.62 | 0 | 0 | 124 | 0 | 0 | 124 | Allowance | Medium | 0.091716
55 | 06 | Wood & Rough Carpentry | LVL beams 3-1/2" x 14" (carport eaves 2 x 25', porch front 22') | 06-250 | 72 | LF | 06-250 | 34 | 0 | 0 | 2448 | 0 | 0 | 2448 | Assumed | Low | 1.8107
56 | 06 | Wood & Rough Carpentry | 6x6 PT posts w/ base & cap, wrapped | 06-260 | 2 | EA | 06-260 | 150 | 0 | 0 | 300 | 0 | 0 | 300 | Measured | Medium | 0.22189
57 | 06 | Wood & Rough Carpentry | ZIP System 7/16" wall sheathing, 4x9 panels | 06-270 | 54 | SHT | 06-270 | 45 | 0 | 0 | 2430 | 0 | 0 | 2430 | Calculated | High | 1.7973
58 | 06 | Wood & Rough Carpentry | ZIP System 5/8" roof sheathing, 4x8 panels | 06-280 | 85 | SHT | 06-280 | 52 | 0 | 0 | 4420 | 0 | 0 | 4420 | Calculated | High | 3.2692
59 | 06 | Wood & Rough Carpentry | ZIP System tape 3.75" x 90' rolls | 06-290 | 20 | RL | 06-290 | 36 | 0 | 0 | 720 | 0 | 0 | 720 | Calculated | High | 0.53254
60 | 06 | Wood & Rough Carpentry | ZIP liquid flash / stretch tape at openings & penetrations | 06-295 | 1 | LS | 06-295 | 350 | 0 | 0 | 350 | 0 | 0 | 350 | Allowance | Medium | 0.25888
61 | 06 | Wood & Rough Carpentry | Structural connectors (truss ties, straps, hangers, post bases) | 06-300 | 1 | LS | 06-300 | 1150 | 0 | 0 | 1150 | 0 | 0 | 1150 | Allowance | Medium | 0.85059
62 | 06 | Wood & Rough Carpentry | Nails, screws, adhesives, sill gasket | 06-310 | 1975.75 | SF | 06-310 | 0.45 | 0 | 0 | 889.0875 | 0 | 0 | 889.0875 | Calculated | High | 0.65761
63 | 06 | Wood & Rough Carpentry | Framing labor - conditioned (walls, trusses, purlins, sheathing) | 06-320 | 1347.5 | SF | 06-320 | 0 | 7.25 | 0 | 0 | 9769.375 | 0 | 9769.375 | Calculated | High | 7.2259
64 | 06 | Wood & Rough Carpentry | Framing labor - porch & carport (beams, posts, trusses, sheathing) | 06-325 | 628.25 | SF | 06-325 | 0 | 3.75 | 0 | 0 | 2355.9375 | 0 | 2355.9375 | Calculated | High | 1.7426
65 | 06 | Wood & Rough Carpentry | Telehandler rental (truss & material set) | 06-340 | 1 | LS | 06-340 | 0 | 0 | 1150 | 0 | 0 | 1150 | 1150 | Allowance | Medium | 0.85059
66 | 07 | Thermal & Moisture Protection | Wall insulation R-21 batts (2x6) | 07-100 | 1261.05 | SF | 07-100 | 0 | 0 | 1.15 | 0 | 0 | 1450.2075 | 1450.2075 | Calculated | High | 1.0726
67 | 07 | Thermal & Moisture Protection | Ceiling insulation blown fiberglass R-38 | 07-110 | 1246.34 | SF | 07-110 | 0 | 0 | 1.45 | 0 | 0 | 1807.193 | 1807.193 | Calculated | High | 1.3367
68 | 07 | Thermal & Moisture Protection | Air sealing package (top plates, penetrations, rim) | 07-115 | 1 | LS | 07-115 | 0 | 0 | 650 | 0 | 0 | 650 | 650 | Allowance | Medium | 0.48077
69 | 07 | Thermal & Moisture Protection | Architectural asphalt shingles, black/charcoal | 07-130 | 27.1775 | SQ | 07-130 | 118 | 92 | 0 | 3206.9404 | 2500.3264 | 0 | 5707.2668 | Calculated | High | 4.2214
70 | 07 | Thermal & Moisture Protection | Hip & ridge cap shingles | 07-140 | 100.884 | LF | 07-140 | 3.25 | 1.25 | 0 | 327.873 | 126.105 | 0 | 453.978 | Calculated | High | 0.33578
71 | 07 | Thermal & Moisture Protection | Ridge vent (over conditioned attic only) | 07-145 | 64.17 | LF | 07-145 | 3.75 | 1.5 | 0 | 240.6375 | 96.255 | 0 | 336.8925 | Assumed | Medium | 0.24918
72 | 07 | Thermal & Moisture Protection | Fiber cement smooth panel siding 4x9, incl. Z-flash | 07-150 | 1444.3654 | SF | 07-150 | 2.15 | 2.35 | 0 | 3105.3857 | 3394.2588 | 0 | 6499.6445 | Calculated | High | 4.8074
73 | 07 | Thermal & Moisture Protection | Panel joint trim / battens | 07-155 | 200 | LF | 07-155 | 1.1 | 1.25 | 0 | 220 | 250 | 0 | 470 | Assumed | Medium | 0.34763
74 | 07 | Thermal & Moisture Protection | Fiber cement T&G siding - porch walls & front gable | 07-160 | 314.6699 | SF | 07-160 | 2.85 | 2.75 | 0 | 896.8092 | 865.3422 | 0 | 1762.1514 | Calculated | Medium | 1.3034
75 | 07 | Thermal & Moisture Protection | Fiber cement T&G porch ceiling (sloped) | 07-170 | 159.7531 | SF | 07-170 | 3.1 | 3.25 | 0 | 495.2346 | 519.1975 | 0 | 1014.4321 | Calculated | High | 0.75032
76 | 07 | Thermal & Moisture Protection | Fiber cement panel ceiling - covered parking (sloped) | 07-180 | 631.1078 | SF | 07-180 | 2.15 | 2.6 | 0 | 1356.8818 | 1640.8803 | 0 | 2997.7622 | Calculated | High | 2.2173
77 | 07 | Thermal & Moisture Protection | Fiber cement vented soffit, 12" | 07-190 | 267.96 | LF | 07-190 | 3.25 | 3 | 0 | 870.87 | 803.88 | 0 | 1674.75 | Assumed | Medium | 1.2387
78 | 07 | Thermal & Moisture Protection | Fiber cement fascia 5/4x6, painted | 07-200 | 267.96 | LF | 07-200 | 2.4 | 2.1 | 0 | 643.104 | 562.716 | 0 | 1205.82 | Calculated | High | 0.89188
79 | 07 | Thermal & Moisture Protection | Fiber cement trim 5/4x4 (corners & opening casings) | 07-210 | 315.337 | LF | 07-210 | 1.75 | 2.1 | 0 | 551.8397 | 662.2077 | 0 | 1214.0475 | Calculated | Medium | 0.89796
80 | 07 | Thermal & Moisture Protection | 5" seamless aluminum gutters | 07-220 | 192.16 | LF | 07-220 | 0 | 0 | 8.5 | 0 | 0 | 1633.36 | 1633.36 | Calculated | High | 1.2081
81 | 07 | Thermal & Moisture Protection | 2x3 aluminum downspouts w/ splash blocks | 07-225 | 42 | LF | 07-225 | 0 | 0 | 8 | 0 | 0 | 336 | 336 | Assumed | Medium | 0.24852
82 | 07 | Thermal & Moisture Protection | Drip edge | 07-230 | 267.96 | LF | 07-230 | 0.85 | 0.4 | 0 | 227.766 | 107.184 | 0 | 334.95 | Calculated | High | 0.24774
83 | 07 | Thermal & Moisture Protection | Starter strip | 07-235 | 201.768 | LF | 07-235 | 0.75 | 0.25 | 0 | 151.326 | 50.442 | 0 | 201.768 | Calculated | High | 0.14924
84 | 07 | Thermal & Moisture Protection | Pipe boots, roof flashing & sealant | 07-240 | 1 | LS | 07-240 | 225 | 150 | 0 | 225 | 150 | 0 | 375 | Allowance | Medium | 0.27737
85 | 07 | Thermal & Moisture Protection | Exterior caulking & sealants | 07-250 | 1 | LS | 07-250 | 450 | 500 | 0 | 450 | 500 | 0 | 950 | Allowance | Medium | 0.70266
86 | 08 | Openings | Window Type A - vinyl sliding 6'-0" x 4'-0" | 08-100 | 5 | EA | 08-100 | 420 | 95 | 0 | 2100 | 475 | 0 | 2575 | Measured | High | 1.9046
87 | 08 | Openings | Window Type B - vinyl casement 6'-0" x 4'-0" | 08-110 | 2 | EA | 08-110 | 925 | 110 | 0 | 1850 | 220 | 0 | 2070 | Measured | High | 1.5311
88 | 08 | Openings | Window Type C - vinyl single hung 2'-0" x 4'-0" | 08-120 | 1 | EA | 08-120 | 215 | 85 | 0 | 215 | 85 | 0 | 300 | Measured | High | 0.22189
89 | 08 | Openings | Window Type D - vinyl single hung 3'-0" x 5'-0" (ganged x3, grids) | 08-130 | 3 | EA | 08-130 | 335 | 95 | 0 | 1005 | 285 | 0 | 1290 | Measured | High | 0.95414
90 | 08 | Openings | Door 01 (R1) exterior entry 4'-0" x 8'-0" w/ sidelite, prehung | 08-200 | 1 | EA | 08-200 | 1950 | 275 | 0 | 1950 | 275 | 0 | 2225 | Measured | Medium | 1.6457
91 | 08 | Openings | Door 09 (R2) exterior 3'-0" x 6'-8" half-lite, prehung | 08-210 | 1 | EA | 08-210 | 520 | 185 | 0 | 520 | 185 | 0 | 705 | Measured | High | 0.52145
92 | 08 | Openings | Door 10 (R5) exterior 3'-0" x 6'-8" flush, prehung | 08-220 | 1 | EA | 08-220 | 365 | 185 | 0 | 365 | 185 | 0 | 550 | Measured | High | 0.4068
93 | 08 | Openings | Doors 02/04/05/06/08 (R3) interior 2'-8" x 6'-8" shaker, prehung | 08-230 | 5 | EA | 08-230 | 195 | 95 | 0 | 975 | 475 | 0 | 1450 | Measured | High | 1.0725
94 | 08 | Openings | Doors 03/07 (R4) interior bypass 6'-0" x 6'-8" 2-panel | 08-240 | 2 | EA | 08-240 | 395 | 145 | 0 | 790 | 290 | 0 | 1080 | Measured | High | 0.79882
95 | 08 | Openings | Hardware - entry handleset & deadbolt (01) | 08-250 | 1 | EA | 08-250 | 215 | 45 | 0 | 215 | 45 | 0 | 260 | Measured | High | 0.19231
96 | 08 | Openings | Hardware - exterior keyed lever & deadbolt (09, 10) | 08-255 | 2 | EA | 08-255 | 95 | 40 | 0 | 190 | 80 | 0 | 270 | Measured | High | 0.1997
97 | 08 | Openings | Hardware - privacy levers (02, 04, 05, 06) | 08-260 | 4 | EA | 08-260 | 32 | 20 | 0 | 128 | 80 | 0 | 208 | Assumed | Medium | 0.15385
98 | 08 | Openings | Hardware - passage lever (08) | 08-265 | 1 | EA | 08-265 | 28 | 20 | 0 | 28 | 20 | 0 | 48 | Assumed | Medium | 0.035503
99 | 08 | Openings | Hardware - bypass pulls & track (03, 07) | 08-270 | 2 | EA | 08-270 | 22 | 10 | 0 | 44 | 20 | 0 | 64 | Measured | High | 0.047337
100 | 08 | Openings | Door stops | 08-275 | 8 | EA | 08-275 | 5 | 4 | 0 | 40 | 32 | 0 | 72 | Calculated | High | 0.053254
101 | 09 | Finishes | 1/2" gypsum board - walls, hang & finish Level 3 | 09-100 | 3760.1334 | SF | 09-100 | 0.58 | 1.55 | 0 | 2180.8774 | 5828.2068 | 0 | 8009.0842 | Calculated | High | 5.9239
102 | 09 | Finishes | Moisture-resistant gypsum premium (baths & laundry) | 09-105 | 955 | SF | 09-105 | 0.18 | 0 | 0 | 171.9 | 0 | 0 | 171.9 | Calculated | Medium | 0.12714
103 | 09 | Finishes | 5/8" gypsum board - ceilings, hang & finish Level 3 | 09-110 | 1395.9008 | SF | 09-110 | 0.72 | 1.75 | 0 | 1005.0486 | 2442.8264 | 0 | 3447.875 | Calculated | High | 2.5502
104 | 09 | Finishes | Drywall accessories (bead, mud, tape, screws) | 09-120 | 4603.602 | SF | 09-120 | 0.12 | 0 | 0 | 552.4322 | 0 | 0 | 552.4322 | Calculated | High | 0.4086
105 | 09 | Finishes | Baseboard 3-1/4" MDF, painted | 09-200 | 387.695 | LF | 09-200 | 1.1 | 1.35 | 0 | 426.4645 | 523.3882 | 0 | 949.8528 | Assumed | Medium | 0.70255
106 | 09 | Finishes | Door casing 2-1/4" MDF, painted | 09-210 | 334.5694 | LF | 09-210 | 0.85 | 1.25 | 0 | 284.384 | 418.2117 | 0 | 702.5957 | Calculated | Medium | 0.51967
107 | 09 | Finishes | Window stool & apron, MDF (drywall returns) | 09-220 | 126.5 | LF | 09-220 | 1.6 | 2.5 | 0 | 202.4 | 316.25 | 0 | 518.65 | Assumed | Medium | 0.38362
108 | 09 | Finishes | Interior paint - walls & ceilings (primer + 2 coats) | 09-230 | 4361.202 | SF | 09-230 | 0.28 | 1.02 | 0 | 1221.1366 | 4448.426 | 0 | 5669.5626 | Calculated | High | 4.1935
109 | 09 | Finishes | Paint interior doors (both faces) | 09-240 | 10 | EA | 09-240 | 18 | 65 | 0 | 180 | 650 | 0 | 830 | Calculated | Medium | 0.61391
110 | 09 | Finishes | Paint interior trim | 09-250 | 771.604 | LF | 09-250 | 0.1 | 0.75 | 0 | 77.1604 | 578.703 | 0 | 655.8634 | Calculated | High | 0.48511
111 | 09 | Finishes | Exterior paint - fiber cement siding, ceilings, soffit | 09-260 | 2509.2429 | SF | 09-260 | 0.32 | 0.95 | 0 | 802.9577 | 2383.7807 | 0 | 3186.7384 | Calculated | Medium | 2.3571
112 | 09 | Finishes | Exterior paint - fascia & trim | 09-265 | 730.27 | LF | 09-265 | 0.08 | 0.65 | 0 | 58.4216 | 474.6755 | 0 | 533.0971 | Calculated | High | 0.3943
113 | 09 | Finishes | Exterior doors paint/finish | 09-270 | 3 | EA | 09-270 | 25 | 85 | 0 | 75 | 255 | 0 | 330 | Measured | High | 0.24408
114 | 09 | Finishes | Interior caulk & touch-up | 09-280 | 1 | LS | 09-280 | 150 | 250 | 0 | 150 | 250 | 0 | 400 | Allowance | Medium | 0.29586
115 | 10 | Specialties | Bath accessories (towel bar, ring, TP holder, hook) | 10-100 | 2 | SET | 10-100 | 140 | 85 | 0 | 280 | 170 | 0 | 450 | Assumed | Medium | 0.33284
116 | 10 | Specialties | Vanity mirrors | 10-110 | 2 | EA | 10-110 | 95 | 45 | 0 | 190 | 90 | 0 | 280 | Measured | High | 0.2071
117 | 10 | Specialties | Closet shelf & rod / laundry & storage shelving | 10-120 | 32 | LF | 10-120 | 9 | 7 | 0 | 288 | 224 | 0 | 512 | Measured | Medium | 0.3787
118 | 10 | Specialties | Tub shower rods | 10-130 | 2 | EA | 10-130 | 30 | 20 | 0 | 60 | 40 | 0 | 100 | Assumed | Medium | 0.073964
119 | 10 | Specialties | House numbers & mailbox | 10-140 | 1 | LS | 10-140 | 175 | 75 | 0 | 175 | 75 | 0 | 250 | Allowance | Medium | 0.18491
120 | 11 | Equipment (Appliances) | Appliances (range, refrigerator, OTR microwave, dishwasher, washer/dryer) | 11-100 | 1 | LS | 11-100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Allowance | High | 0
121 | 11 | Equipment (Appliances) | Appliance installation & hookups (cords, DW, ice maker, OTR vent) | 11-110 | 1 | LS | 11-110 | 85 | 350 | 0 | 85 | 350 | 0 | 435 | Allowance | Medium | 0.32175
122 | 12 | Casework & Countertops | Base cabinets - frameless, shaker doors | 12-100 | 11.7 | LF | 12-100 | 285 | 45 | 0 | 3334.5 | 526.5 | 0 | 3861 | Measured | Medium | 2.8558
123 | 12 | Casework & Countertops | Wall cabinets - frameless, shaker doors | 12-110 | 9.4 | LF | 12-110 | 215 | 40 | 0 | 2021 | 376 | 0 | 2397 | Measured | Medium | 1.7729
124 | 12 | Casework & Countertops | Tall pantry cabinet 30" x 24" x 84" | 12-120 | 1 | EA | 12-120 | 875 | 85 | 0 | 875 | 85 | 0 | 960 | Measured | Low | 0.71006
125 | 12 | Casework & Countertops | Cabinet fillers, finished ends, island back panel | 12-125 | 1 | LS | 12-125 | 350 | 100 | 0 | 350 | 100 | 0 | 450 | Allowance | Medium | 0.33284
126 | 12 | Casework & Countertops | Bath vanities 30" frameless shaker | 12-130 | 2 | EA | 12-130 | 425 | 85 | 0 | 850 | 170 | 0 | 1020 | Measured | Medium | 0.75444
127 | 12 | Casework & Countertops | Laminate countertops (post-form/custom) | 12-200 | 50.16 | SF | 12-200 | 22 | 9 | 0 | 1103.52 | 451.44 | 0 | 1554.96 | Calculated | Medium | 1.1501
128 | 12 | Casework & Countertops | Laminate 4" backsplash | 12-210 | 22.52 | LF | 12-210 | 6 | 3 | 0 | 135.12 | 67.56 | 0 | 202.68 | Calculated | Medium | 0.14991
129 | 22 | Plumbing | Plumbing rough-in (under-slab DWV, PEX supply, top-out) | 22-100 | 13 | EA | 22-100 | 220 | 480 | 0 | 2860 | 6240 | 0 | 9100 | Calculated | Medium | 6.7308
130 | 22 | Plumbing | Kitchen sink SS 33" drop-in w/ chrome pull-down faucet | 22-110 | 1 | EA | 22-110 | 425 | 0 | 0 | 425 | 0 | 0 | 425 | Measured | High | 0.31435
131 | 22 | Plumbing | Lavatory (drop-in) w/ chrome faucet & drain | 22-120 | 2 | EA | 22-120 | 195 | 0 | 0 | 390 | 0 | 0 | 390 | Measured | High | 0.28846
132 | 22 | Plumbing | Water closet, elongated 2-pc w/ seat | 22-130 | 2 | EA | 22-130 | 285 | 0 | 0 | 570 | 0 | 0 | 570 | Measured | High | 0.4216
133 | 22 | Plumbing | Bathtub 60" w/ chrome tub/shower valve & trim | 22-140 | 2 | EA | 22-140 | 520 | 150 | 0 | 1040 | 300 | 0 | 1340 | Measured | High | 0.99112
134 | 22 | Plumbing | Tub surround, 3-pc acrylic | 22-145 | 2 | EA | 22-145 | 375 | 225 | 0 | 750 | 450 | 0 | 1200 | Measured | High | 0.88757
135 | 22 | Plumbing | Water heater 50 gal electric w/ pan, exp. tank, T&P drain | 22-150 | 1 | EA | 22-150 | 925 | 350 | 0 | 925 | 350 | 0 | 1275 | Measured | Medium | 0.94305
136 | 22 | Plumbing | Washer box, ice maker box, (2) frost-free hose bibs | 22-160 | 1 | LS | 22-160 | 190 | 0 | 0 | 190 | 0 | 0 | 190 | Measured | High | 0.14053
137 | 22 | Plumbing | Fixture trim-out labor | 22-190 | 7 | EA | 22-190 | 0 | 145 | 0 | 0 | 1015 | 0 | 1015 | Calculated | High | 0.75074
138 | 22 | Plumbing | Plumbing permit & inspections | 22-195 | 1 | LS | 22-195 | 0 | 0 | 275 | 0 | 0 | 275 | 275 | Allowance | Medium | 0.2034
139 | 23 | HVAC | 2-ton split heat pump w/ air handler & 5 kW heat strip | 23-100 | 1 | EA | 23-100 | 4650 | 0 | 0 | 4650 | 0 | 0 | 4650 | Measured | Medium | 3.4393
140 | 23 | HVAC | Duct system (plenum, R-8 flex, registers, returns) | 23-110 | 1347.5 | SF | 23-110 | 1.35 | 1.1 | 0 | 1819.125 | 1482.25 | 0 | 3301.375 | Calculated | High | 2.4418
141 | 23 | HVAC | HVAC installation, line set, condensate, pad, thermostat, start-up | 23-120 | 1 | LS | 23-120 | 650 | 2600 | 0 | 650 | 2600 | 0 | 3250 | Allowance | Medium | 2.4038
142 | 23 | HVAC | Bath exhaust fans, ducted to exterior | 23-130 | 2 | EA | 23-130 | 95 | 125 | 0 | 190 | 250 | 0 | 440 | Measured | High | 0.32544
143 | 23 | HVAC | Dryer vent & wall cap | 23-140 | 1 | EA | 23-140 | 55 | 110 | 0 | 55 | 110 | 0 | 165 | Assumed | Medium | 0.12204
144 | 23 | HVAC | Microwave/range vent duct to exterior | 23-150 | 1 | EA | 23-150 | 65 | 125 | 0 | 65 | 125 | 0 | 190 | Assumed | Medium | 0.14053
145 | 23 | HVAC | Mechanical permit | 23-160 | 1 | LS | 23-160 | 0 | 0 | 175 | 0 | 0 | 175 | 175 | Allowance | Medium | 0.12944
146 | 26 | Electrical | 200A service: meter/main, panel, grounding, surge protection | 26-100 | 1 | LS | 26-100 | 1750 | 1250 | 0 | 1750 | 1250 | 0 | 3000 | Assumed | Medium | 2.2189
147 | 26 | Electrical | Branch rough-in wiring - conditioned (AFCI/GFCI, boxes, wire) | 26-110 | 1347.5 | SF | 26-110 | 1.55 | 2.1 | 0 | 2088.625 | 2829.75 | 0 | 4918.375 | Calculated | High | 3.6379
148 | 26 | Electrical | Branch rough-in wiring - porch & carport | 26-115 | 628.25 | SF | 26-115 | 0.45 | 0.65 | 0 | 282.7125 | 408.3625 | 0 | 691.075 | Calculated | High | 0.51115
149 | 26 | Electrical | Devices: receptacles, switches, GFCI, plates | 26-120 | 64 | EA | 26-120 | 7 | 18 | 0 | 448 | 1152 | 0 | 1600 | Assumed | Low | 1.1834
150 | 26 | Electrical | Dedicated appliance/equipment circuits | 26-130 | 8 | EA | 26-130 | 95 | 125 | 0 | 760 | 1000 | 0 | 1760 | Calculated | Medium | 1.3018
151 | 26 | Electrical | Smoke/CO combination detectors, hardwired, interconnected | 26-140 | 4 | EA | 26-140 | 48 | 30 | 0 | 192 | 120 | 0 | 312 | Assumed | Medium | 0.23077
152 | 26 | Electrical | LED recessed 6" wafer lights | 26-300 | 23 | EA | 26-300 | 24 | 40 | 0 | 552 | 920 | 0 | 1472 | Measured | Medium | 1.0888
153 | 26 | Electrical | Pendant lights over island | 26-310 | 2 | EA | 26-310 | 120 | 55 | 0 | 240 | 110 | 0 | 350 | Measured | High | 0.25888
154 | 26 | Electrical | Ceiling fans w/ light kit & fan-rated box | 26-320 | 3 | EA | 26-320 | 175 | 85 | 0 | 525 | 255 | 0 | 780 | Measured | High | 0.57692
155 | 26 | Electrical | Vanity lights | 26-325 | 2 | EA | 26-325 | 85 | 45 | 0 | 170 | 90 | 0 | 260 | Measured | High | 0.19231
156 | 26 | Electrical | Exterior lights (6 soffit downlights, front door sconce, rear entry light) | 26-330 | 8 | EA | 26-330 | 55 | 50 | 0 | 440 | 400 | 0 | 840 | Assumed | Medium | 0.6213
157 | 26 | Electrical | Low-voltage (data/TV 4 drops, doorbell) | 26-340 | 1 | LS | 26-340 | 225 | 375 | 0 | 225 | 375 | 0 | 600 | Allowance | Medium | 0.44379
158 | 26 | Electrical | Electrical permit | 26-350 | 1 | LS | 26-350 | 0 | 0 | 225 | 0 | 0 | 225 | 225 | Allowance | Medium | 0.16642
159 | 32 | Exterior Improvements | Concrete driveway 4", 12' wide (lot + 10' ROW apron) | 32-100 | 1548.96 | SF | 32-100 | 3.35 | 3.9 | 0 | 5189.016 | 6040.944 | 0 | 11229.96 | Measured | Medium | 8.3062
160 | 32 | Exterior Improvements | Concrete apron at covered parking (5' + 4' strips) | 32-110 | 216 | SF | 32-110 | 3.35 | 3.9 | 0 | 723.6 | 842.4 | 0 | 1566 | Measured | High | 1.1583
161 | 32 | Exterior Improvements | Front walk / landing pad | 32-120 | 62.4 | SF | 32-120 | 3.35 | 3.9 | 0 | 209.04 | 243.36 | 0 | 452.4 | Measured | Medium | 0.33462
162 | 32 | Exterior Improvements | Driveway culvert & headwalls (if open-ditch street) | 32-130 | 1 | LS | 32-130 | 0 | 0 | 1200 | 0 | 0 | 1200 | 1200 | Allowance | Low | 0.88757
163 | 32 | Exterior Improvements | Shrubs, 3 gal (planting bed along west wall) | 32-200 | 12 | EA | 32-200 | 28 | 15 | 0 | 336 | 180 | 0 | 516 | Measured | Medium | 0.38166
164 | 32 | Exterior Improvements | Bed prep, edging & mulch | 32-205 | 256.68 | SF | 32-205 | 0.55 | 0.45 | 0 | 141.174 | 115.506 | 0 | 256.68 | Measured | High | 0.18985
165 | 32 | Exterior Improvements | Shade tree, 30 gal | 32-207 | 1 | EA | 32-207 | 275 | 125 | 0 | 275 | 125 | 0 | 400 | Measured | High | 0.29586
166 | 32 | Exterior Improvements | Sod - front & east side yards | 32-210 | 1700 | SF | 32-210 | 0.55 | 0.3 | 0 | 935 | 510 | 0 | 1445 | Assumed | Medium | 1.0688
167 | 32 | Exterior Improvements | Seed & straw - balance of disturbed lot | 32-215 | 3360.16 | SF | 32-215 | 0.08 | 0.06 | 0 | 268.8128 | 201.6096 | 0 | 470.4224 | Calculated | Medium | 0.34795
168 | 33 | Utilities | Water service 1" (meter to house) | 33-100 | 45 | LF | 33-100 | 0 | 0 | 14 | 0 | 0 | 630 | 630 | Assumed | Low | 0.46598
169 | 33 | Utilities | Sewer service 4" PVC w/ cleanouts | 33-110 | 50 | LF | 33-110 | 0 | 0 | 26 | 0 | 0 | 1300 | 1300 | Assumed | Low | 0.96154
170 | 33 | Utilities | Water/sewer tap, meter & impact fees (municipal) | 33-120 | 1 | LS | 33-120 | 0 | 0 | 3500 | 0 | 0 | 3500 | 3500 | Allowance | Low | 2.5888
171 | 33 | Utilities | Underground electric service lateral | 33-130 | 60 | LF | 33-130 | 0 | 0 | 16 | 0 | 0 | 960 | 960 | Assumed | Low | 0.71006
172 | 33 | Utilities | Utility company service/connection charges | 33-140 | 1 | LS | 33-140 | 0 | 0 | 800 | 0 | 0 | 800 | 800 | Allowance | Low | 0.59172
|  |  | TOTAL DIRECT COST | [7 empty] | 112469.3579 | 100225.2778 | 42988.058 | 255682.6937

## Reconciliation
Check | Takeoff / Workbook Qty | Model / Reference Qty | Unit | Variance | Variance % | Reason / Explanation | Review Status
Conditioned area vs. design notes (1,352 gsf) | 1347.5 | 1352 | SF | -4.5 | -0.3328% | Takeoff uses dimensioned 21'-0" x 64'-2". Notes area likely measured to outside of sheathing/siding. Within tolerance. | OK
Porch area vs. design notes (117 gsf) | 124.25 | 117 | SF | 7.25 | 6.197% | Takeoff = slab under porch incl. side-wall footprint (21' x 5'-11"); notes = clear area between porch walls (~19.8' x 5.92'). Not an error. | Explained
Covered parking vs. design notes (504 gsf) | 504 | 504 | SF | 0 | 0% | 21'-0" x 24'-0" dimensioned. | OK
Total under roof vs. design notes (1,973 gsf) | 1975.75 | 1973 | SF | 2.75 | 0.1394% | Dimensions sum to 70'-1" vs 70'-0" overall (1" chain rounding) - 0.1%. | OK
Slab footprint: takeoff vs. model | 1975.75 | 1975.75 | SF | 0 | 0% | Same dimension source. | OK
Exterior 2x6 wall length: takeoff vs. model | 182.17 | 182.17 | LF | 0 | 0% | Includes porch side walls (W/E walls run 70'-1"). | OK
Interior partition length: takeoff vs. model | 138.56 | 138.56 | LF | 0 | 0% | Both from scaled partition coordinates (calibrated 18.81 px/ft). Partition locations are not dimensioned on A101 - scaled tolerance about +/-3". | Review
Window count: takeoff vs. model vs. A701 schedule (11) | 11 | 11 | EA | 0 | 0% | Schedule 11 = plan tags 11 = elevations 11 (A x5 west, B x2 east, C x1 rear, D x3 front). | OK
Exterior doors: takeoff vs. model (A701 01, 09, 10) | 3 | 3 | EA | 0 | 0% |  | OK
Interior doors: takeoff vs. model (A701 02-08) | 7 | 7 | EA | 0 | 0% |  | OK
Roof area (sloped): takeoff vs. model | 2470.6783 | 2470.76 | SF | -0.081738 | -0.003308% | Both include ASSUMED 12" eave & rake overhangs. | OK
Truss count: takeoff vs. model | 25 | 25 | EA | 0 | 0% | 48" O.C. per design notes (see RFI-06). | OK
Light fixtures (cans + pendants + fans): takeoff vs. model RCP count | 28 | 28 | EA | 0 | 0% | Exterior soffit/wall lights (26-330) are counted separately and are not on the RCP. | OK
Overall length: dimension chain vs. overall dim 70'-0" | 70.083 | 70 | FT | 0.083 | 0.1186% | 6'-10" + 13'-5" + 9'-10" + 11'-2" + 22'-11" + 5'-11" = 70'-1". 1" discrepancy on A101 - used the chain. | Explained
Plan calibration: 21'-0" vs. vertical 70'-0" (px/ft) | 18.81 | 18.74 | px/ft | 0.07 | 0.3735% | Horizontal vs. vertical scale agreement 0.4% - scan/plot distortion negligible. | OK